## ALL
Category |  | 1 | Task name | Comment | Responsibility | Location | Start | Finish | Recurrance/frequency
[9 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
STAKEHOLDER ENGAGEMENT PLAN (SEP)
EXTERNAL STAKEHOLDERS | 1 All external stakeholders (all-level authorities; local communities; vulnerable groups; other parties: NGOs, educational, mass media and community based organizations, etc. | 1.1 | Inform on the project implementation status (presentations; booklets and progress leaflets; online news, records of meetings) |  | BHCT Project Team / Stakeholder Management Team / Communication Dept | Local government offices, library or other public facilities having adequate space |  |  |  | x |  |  |  | x
|  | 1.2 | Collect opinions and concerns during annual public meetings; |  | BHCT Project Team / Stakeholder Management Team / Communication Dept | Local government offices, library or other public facilities having adequate space |  |  |  | x |  |  |  | x
|  | 1.3 | Publicly disclose Project documentation (SEP, ESAP, SIP, NTS) |  | BHCT Project Team / Stakeholder Management Team / Communication Dept | Local government offices, library or other public facilities having adequate space |  |  |  | x |  |  |  | x
|  | 1.4 | Publicly disclose relevant Project updates (Post news on the Company’s website) |  | BHCT Project Team / Stakeholder Management Team / Communication Dept | Local government offices, library or other public facilities having adequate space |  |  |  | x |  |  |  | x
|  | 1.5 | Register, analyse and address comments submitted online |  | BHCT Project Team / Stakeholder Management Team / Communication Dept | Local government offices, library or other public facilities having adequate space |  |  |  | x |  |  |  | x
| 2 Local authorities | 2.1 | Jointly organize open doors and annual meetings to collect community feedback | to organize meeting at school / library; bus tour around terminal; photo site visit on the beach; representation from port authority / city needed; once a year at least; summer cinema - to be used as ommunication chanel - to arrange a company who is experienced CSR Info (to check), they know how to perform the stakeholders dialogue; CEC to be involved | BHCT Project Team and Communication Dept | Project site, company offices, authorities offices |  |  |  | x |  |  |  | x
|  | 2.2 | Develop plans to support commitments to invest in the wider port area - Stogi beach, Przerorobka district, etc. (Presentations / reports) | Busole | BHCT Project Team and Communication Dept | Project site, company offices, authorities offices |  |  |  | x |  |  |  | x
| 3 National and regional authorities, in particular, inspection agencies responsible for environmental protection and health and safety | 3.1 | Submit regular reports with the frequency dictated by the authorities on compliance with national legislation and permits | RDOŚ to send required reports based on environmental decision, re. Birds, bats, mammals; agreemnets with ornitologist and chiroptorologyst - onging; T3 decision - we need to continue all requirements from T2 environmental decision; what kind of reports - Karolina to send | BHCT Project Team and Safety | Project site, company offices, authorities offices |  |  |  | x
| 4 Focused stakeholder engagement with Chief of the Seal Sanctuary of the Hel Marine Station of the Institute of Oceanography of Gdansk University | 4.1 | Discuss the proposed deviations from the JNCC protocol and their effectiveness in protection of marine mammals from project activity (meetings and consultations / minutes from the meeting) | Budimex / DEME is consulting soft-start procedure (palling procedure); they are to send notes re. Changing decision; the meeting was held (when?) | BHCT Project team managed by external companies Budimex and DEME / Consultant | Hel marine Station of the Institute Oceanography of Gdansk Universi or similar organization | [7 empty] | x
| 5 Focused stakeholder engagement with local communities and vulnerable groups living in the project area | 5.1 | Analyse the local socio-economic conditions in the project area of influence, focus on vulnerable groups (presentations, leaaflets, community meetings) | Social - economic Report from Arup (to check local communities pointed in the report, local businesses and be in touch with them) | BHCT representative / Consultant | Local communieties (library, community centers, local authority offices) | [7 empty] | x
|  | 5.2 | Public consultation meetings to consult the local communities about their needs, views/concerns on project implementation and impacts provided via community initiatives (project leaflets) | to invite for open doors; meeting at school; questions prior the meeting, QR code with questions (2 weeks for analysing) | Project team (questins) / Communications (organizning) | Company's representatives visiting local communities | [7 empty] | x
|  | 5.3 | External grievance mechanism and targeted group meetings, as necessary (Public grievance forms (distributed, published in the local media, posted on the Company’s web-site for printing out / downloading / electronic submitting) | the register to be managed by who? Claims dept to keep the register in place : Michal to discuss it with Grzegorz; | Communications (tool) / Claims (register and coordination) | Company's representatives visiting local communities | [5 empty] | x
| 6 Focused stakeholder engagement with local businesses at Stogi beach | 6.1 | Individual meetings to notify the business owners at Stogi beach of the potential impacts from the Project that could impact the number of beach goers | posters re. open meeting for local business; questions before the meeting | Company representative / Project Team / Communications / Claims coordinator | Company offices | [7 empty] | x
|  | 6.2 | Update regularly on planned activities | posters, leaflets, no sending info becouse of RODO (GDPR) | Company representative / Project Team / Communications / Claims coordinator | Company offices | [7 empty] | x
|  | 6.3 | Set up communication channels for businesses to report issues with their operations to BHCT | posters with contact details for complains; stand by duty at DCT for stakeholders (1 hr at week for face to face mtg); - formularz zażaleń, dedykowany adres e-mail, strona www | Company representative / Project Team / Communications / Claims coordinator | Company offices | [7 empty] | x
| 7 Other businesses in the project area | 7.1 | Formal meetings to discuss increased traffic flows from T3 | implement on demand | Company representative / Project Team / Communications | Company offices / Local authority offices | [7 empty] | x
|  | 7.2 | Notifications on works stages and planned activities (letter, notification, company website) |  | Company representative / Project Team / Communications | Company offices / Local authority offices | [7 empty] | x
| 8 Stogi beach visitors | 8.1 | Notify beach goers of any potential impacts from the Project (visual impacts, noise, light and water pollution,congestion of traffic coming into the area), during construction and operation (leaflets) | summer cinema to present info prior the movie; leaflets and posters, QR code questionaires | Project team / communications | Project site, company website | [7 empty] | x
|  | 8.2 | Notify the public about DCT external Grievance Mechanism (public announcements at notice boards) | leaflets, webpage, posters | Project team / communications | Project site, company website | [7 empty] | x
|  | 8.3 | Post updated on the Project, specifically upcoming construction activities, on the Company’s website |  | Project team / communications | Project site, company website | [7 empty] | x
| 9 Other parties: NGOs, cultural, educational, mass media and community based organizations, military fans etc. | 9.1 | Booklets and progress leaflets | WWF / Greenpeace -> info the first meetg was held on xx; they know how to contatc DCT | Company representative / Projet team / Communications | Project site, company offices | [6 empty] | x
|  | 9.2 | Individual meetings (on specific matters) |  | Company representative / Projet team / Communications | Project site, company offices | [6 empty] | x
|  | 9.3 | Email or phone communication (to be properly registered) | all info in the project folder; Klaudia to create folder; to discuss with Adrian how it should look like; minutes from the meeting as a proof | Company representative / Projet team / Communications | Project site, company offices | [6 empty] | x
INTERNAL STAKEHOLDERS | 10 Shareholders of the Company | 10.1 | Inform, consult, and involve in strategic decision making processes via constant reporting on project implementation status | Monthly Steering committee/ Management Mtg, SBM (Qarterly) | Company Management | Company or shareholders headqarter | [7 empty] | x
|  | 10.2 | Annual reports on project implementation status | Monthly Steering committee/ Management Mtg, SBM (Qarterly) | Company Management | Company or shareholders headqarter | [7 empty] | x
|  | 10.3 | Project implementation status discussed on direct meetings | Monthly Steering committee/ Management Mtg, SBM (Qarterly) | Company Management | Company or shareholders headqarter | [7 empty] | x
|  | 10.4 | Project implementation status discussed on shareholders board meetings | Monthly Steering committee/ Management Mtg, SBM (Qarterly) | Company Management | Company or shareholders headqarter | [7 empty] | x
| 11 Company employees | 11.1 | Inform employees about the Company Project plans in relation to labour issues LinkedIn, Intranet (screen), internal movies (Charles) | Intranet, MR, CEO movies, events, mtgs with unions | Project team and Communications / HR | Project site, company office, company website. Intranet / MR | [7 empty] | x
|  | 11.2 | Inform employees about the actual impacts on the local environment and communities | Intranet (dedicated T3 section), MR, CEO movies, events, mtgs with unions / publish environmental report | Project team and Communications / HR | Project site, company office, company website. Intranet / MR | [7 empty] | x
|  | 11.3 | Include reference to the external grievance mechanism | Intranet, MR, CEO movies, events, mtgs with unions, to put the mechanism on Intranet | Project team and Communications / HR | Project site, company office, company website. Intranet / MR | [7 empty] | x
|  | 11.4 | Inform employees about the internal Project development issues, success and difficulties | Intranet, MR, CEO movies, events, mtgs with unions | Project team and Communications / HR | Project site, company office, company website. Intranet / MR |  |  |  |  | x |  |  | x
| 12 Contractors (on site) | 12.1 | Inform all contractors about DCT and EBRD requirements and commitments under the ESAP, SEP and otherrelevance management plans | general contractor to inform how to contact other T3 contractors and sub-contractors | Projct team / Contractor's representative | company office / contractor office / formal communiaction |  |  |  | x |  | x |  | x
|  | 12.1.1 | Direct meetings and reporting | Michal to think about it :) point in the report how it was done (general Contractor to answer) | Company's representative / Contractor's representative | company office / contractor office / formal communiaction |  |  |  | x |  | x |  | x
|  | 12.1.2 | Contract requirements to be reflected in EPC contract as relevant based on DCT commitments under the ESAP | EPC contract is signed | Company's representative / Contractor's representative | company office / contractor office / formal communiaction |  |  |  | x |  | x |  | x
|  | 12.1.3 | Monitoring, inspections and audits | to check in SEP requiremnets | Company's representative / Contractor's representative | company office / contractor office / formal communiaction |  |  |  | x |  | x |  | x
|  | 12.1.4 | Training and supervision | to check in SEP requiremnets | Company's representative / Contractor's representative | company office / contractor office / formal communiaction |  |  |  | x |  | x |  | x
|  | 12.1.5 | Progress and incident reports | to check in SEP requiremnets | Company's representative / Contractor's representative | company office / contractor office / formal communiaction |  |  |  | x |  | x |  | x
| 13 Employees of the contractors | 13.1 | Inform the employees and contractors about labours and safety issues via direct meetings and information notes | Budimex to end the proof that it is performed correctly | Company's EHS officer | Construction camps / contractors office | [7 empty] | x
|  | 13.2 | Training to include reference to workers grievance management system | Budimex to end the proof that it is performed correctly | Company's EHS officer | Construction camps / contractors office | [7 empty] | x
|  | 13.3 | Training on project impacts and requirements to be organised as part of induction training for all employees | Budimex to end the proof that it is performed correctly | Company's EHS officer | Construction camps / contractors office | [7 empty] | x
|  | 13.4 | Training to refer to the external grievance management system. | Budimex to end the proof that it is performed correctly | Company's EHS officer | Construction camps / contractors office | [7 empty] | x
Note on D9: Support: to organize meeting at school / library; bus tour around terminal; photo site visit on the beach; representation from port authority / city needed; once a year at least; summer cinema - to be used as ommunication chanel - to arrange a company who is experienced CSR Info (to check), they know how to perform the stakeholders dialogue; CEC to be involved
Note on D10: Support: Busole - keep inform
Note on D11: Support: RDOŚ to send required reports based on environmental decision, re. Birds, bats, mammals; agreemnets with ornitologist and chiroptorologyst - onging; T3 decision - we need to continue all requirements from T2 environmental decision; what kind of reports - Karolina to send
Note on B24: Support: dodać komunikaty prasowe

## Social monitoring
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | ESAP | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 14 Social Monitoring | 13.4 | Social Monitoring ESAP (including regular media search and updates from local authorities, updates from the grievance management register, and visual inspections) | Communication | [7 empty] | x
|  | DATE | REMARKS
|  | (29.08.2022) | E-mail communication re. beginning of T3 construction was sent to district councils, neighbourhood libraries, Gdansk port authority,Social Media groups of Stogi District
|  | (31.08.2022) | Face to face talks with Chairmans of the local district council / events related to Grant Competition Busole (Welfare Senior Home "Ostoja" in Stogi district)
|  | (06.09.2022) | Direct phone call - Chairman of Stogi District Council (in relation to informational posters placed in a district, asking about any comments form people - till now no comments and questions)
|  | (06.09.2022) | Direct phone call - Library in Stogi (in relation to informational posters placed in a district, asking about any comments form people - till now no comments and questions)
|  | (06.09.2022) | Direct phone call - Spokesperson of Port Authorithy (in relation to opinion from people re. T3 construction)
|  | (08.09.2022) | Face to face talks with Chairmans of the local district council / events related to Grant Competition Busole (Promary school no.61 in Przerobka district)
|  | (23.09.2022) | Meetings with local community (district councils)
|  | (16.11.2022) | Economical report TVP (regional TV) https://gdansk.tvp.pl/64557614/odc-16112022
|  | (28.11.2022) | News in Panorama (regional TV) https://gdansk.tvp.pl/64778519/rozbudowa-terminala-baltic-hub
|  | (28.11.2022) | Groundbreaking ceremony - event for media and external stakeholders https://www.gospodarkamorska.pl/w-baltic-hub-w-porcie-gdansk-startuje-budowa-trzeciego-nabrzeza-kontenerowego-67957
|  | (30.11.2022) | Economical report TVP (regional TV) https://gdansk.tvp.pl/64831323/odc-30112022
|  | MJ (08.12.2022) | Participation in Christmas meeting organized by Primary School no. 61 with Przerobka district concil presence
|  | (15.12.2022) | Participation in Christmas meeting organized by Primary School no. 72 with Stogi district council presence
|  | (22.12.2022) | Mtg with Directorate of City Development Gdansk
|  | (22.12.2022) | Participation in Christmas meeting organized by "Ostoja" social welfare home with Stogi district council presence
|  | (04.01.2023) | News in TVP (regional TV) re. Status of T3 construction https://gdansk.tvp.pl/65477788/baltic-hub-sie-powieksza-modernizacja-terminalu-nabiera-tempa
|  | daily / ongoing | Grievance monitoring - 12 complaints as till December 2023
|  | monthly / ongoing | Stogi Beach - visual check
|  | daily / ongoing | Media monitoring by IMM (Instytut Monitorowania Mediów)
|  | monthly / ongoing | Grievance register available on website and updated regulary Link: https://baltichub.com/wp-content/uploads/2023/09/T3-complaints-register_2.pdf

## 1.1
Category |  | Nr. | Task name | Responsibility | Start | Finish | [6 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 1 All external stakeholders (all-level authorities; local communities; vulnerable groups; other parties: NGOs, educational, mass media and community based organizations, etc. | 1.1 | Inform on the project implementation status (presentations; booklets and progress leaflets; online news, records of meetings) | BHCT Project Team / Stakeholder Management Team / Communication Dept |  |  |  | x |  |  |  | x
|  | DATE | REMARKS
Inform about T3 project status by means of: - brochures and leaflets describing works progress are created by marketing & communication dept - BHCT Gdansk website (online news) - records of meetings
|  | 12.2021 | Subpage dedicated to T3 project is implemented on main BHCT website https://baltichub.com/inwestycje/projekt-t3 https://baltichub.com/en/investments/project-t3
|  | (23.09.2022) | Meetings with local community (district councils)
|  | (29.08.2022) | Posters and leaflets re. beginning of T3 construction were prepared and posted on notice boards in neighbourhood districts, in the library in Stogi and Przerobka
|  | (29.08.2022) | E-mail communication re. beginning of T3 construction was sent to district councils, neighbourhood libraries, Gdansk port authority, Social Media groups of Stogi District
|  | (08.07.2022) | Post on the T3 subpage and mainpage re. Selecting contractors was published: https://dctgdansk.pl/en/news/dct-gdansk-selects-contractors-to-begin-works-for-the-t3-expansion-project/
|  | (29.08.2022) | Post on the T3 subpage and mainpage re. Purchase of semi-automated RTG cranes was published: https://dctgdansk.pl/en/news/purchase-of-semi-automated-rtg-cranes/
|  | (08.09.2022) | Post on the T3 subpage and mainpage of T3 construction informational poster
|  | (31.08.2022) | Face to face talks with Chairmans of the local district council / events related to Grant Competition Busole (Welfare Senior Home "Ostoja" in Stogi district)
|  | (08.09.2022) | Face to face talks with Chairmans of the local district council / events related to Grant Competition Busole (Promary school no.61 in Przerobka district)
|  | (06.09.2022) | Direct phone call - Chairman of Stogi District Council (in relation to informational posters placed in a district, asking about any comments form people - till now no comments and questions)
|  | (06.09.2022) | Direct phone call - Library in Stogi (in relation to informational posters placed in a district, asking about any comments form people - till now no comments and questions)
|  | (06.09.2022) | Direct phone call - Spokesperson of Port Authorithy (in relation to opinion from people re. T3 construction)
|  | (28.11.2022) | Groundbreaking ceremony - event for media and external stakeholders https://www.gospodarkamorska.pl/w-baltic-hub-w-porcie-gdansk-startuje-budowa-trzeciego-nabrzeza-kontenerowego-67957
|  | (08.12.2022) | Participation in Christmas meeting organized by Primary School no. 61 with Przerobka district concil presence
|  | (22.12.2022) | Participation in Christmas meeting organized by "Ostoja" social welfare home with Stogi district council presence
|  | (15.12.2022) | Participation in Christmas meeting organized by Primary School no. 72 with Stogi district council presence
|  | (16.11.2022) | Economical report TVP (regional TV) https://gdansk.tvp.pl/64557614/odc-16112022
|  | (28.11.2022) | News in Panorama (regional TV) https://gdansk.tvp.pl/64778519/rozbudowa-terminala-baltic-hub
|  | (30.11.2022) | Economical report TVP (regional TV) https://gdansk.tvp.pl/64831323/odc-30112022
|  | Nov 2022 | article LogisticsNews
|  | (04.01.2023) | News in TVP (regional TV) re. Status of T3 construction https://gdansk.tvp.pl/65477788/baltic-hub-sie-powieksza-modernizacja-terminalu-nabiera-tempa
|  | JAN/FEB 2023 | Leaflets and posters campaign re. stage of construction and grievance mechanism
|  | 10.02.2023 | Posters and leaflets re. status of T3 construction were prepared and posted on notice boards in neighbourhood districts, in the library in Stogi and Przerobka
|  | 03.04.2023 | II Distric Grant Busole - announcement https://dctgdansk.pl/aktualnosci/baltic-hub-startuje-z-druga-edycja-konkursu-grantowego-busole/
|  | 17.04.2023 | Meeting with Distric Councils
|  | April-May 2023 | Correspondence with Distric Council and citizens re. Noise (answering complaints) Summary of complaints available here: https://dctgdansk.pl/wp-content/uploads/2023/06/T3-complaints-register_2.pdf
|  | 02.06.2023 | Correspondence and direct talks with District Council re. Empty Pond revitalization (this pond is close to Stogi Beach and T3 investment) and CHristmas Tree financig
|  | 31.05.2023 | II Distric Grant Busole results https://dctgdansk.pl/aktualnosci/ii-edycja-konkursu-grantowego-busole-rozstrzygnieta/ https://dctgdansk.pl/en/news/results-of-the-2nd-edition-of-the-busole-grant-competition/
|  | 25.06.2023 | Supporting the sport event (run arond the Empty Pond) for Stogi District Citizens (this pond is close to Stogi Beach and T3 investment)
|  | 28.05.2023 | article gdansk.pl re. T3 construction https://www.gdansk.pl/wiadomosci/Stogi-Koniec-glosnego-uporczywego-palowania,a,243946
|  | 26.06.2023 | Poster informing/ reminding re. Greviance form (placed in Budimex social rooms, on construction site, on the beach
|  | 30.06.2023 | Sustainability Report for 2022 as a summary of BHCT annual performance - publication https://dctgdansk.pl/csr/raport-zrownowazonego-rozwoju/
|  | June 2023 | article DopravniNoviny
|  | July 2023 | Rozbudowa Baltic Hubu jeszcze trochę potrwa. Jej koszt wyniesie około 2 mld ¦ PulsGdanska.pl
|  | July 2023 | Article wnp.pl re. T3 construction
|  | ongoing | Status of the T3 in all company presentations
|  | July-August 2023 | Sumemr cinema and sport activities at Stogi beach for residents
|  | (2023-09-01) | Marine fest for local residents - open doors https://www.youtube.com/watch?v=mrB37Kas6Kw
|  | (2023-10-01) | T3 status movie (September 2023), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=usPCiuBqAok FB: https://fb.watch/nVSUVXpAi3/ LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7120719815895359488
|  | (2023-10-27) | Meeting with District Councils re. T3 status and current issues 27.10.2023
|  | (2023.11.29) | Economical report TVP (regional TV) https://gdansk.tvp.pl/74456119/odc-29112023
|  | (2023-12-08) | T3 posters - status of the construction placed in local districts
|  | (2024-06-08) | Festival organised by Stogi District Council for residents - BHCT informational point, eco workshop for kids, iceream; leaflets and poster with T3 status
|  | (2024-06-08) | Festival organised by Przerobka District Council for residents - BHCT sponsored theatre play for children
|  | 2024-01-01 | T3 status movie (January 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=4QIIHJqkOBE
|  | 2024-02-01 | T3 status movie (February 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=4c5Mz9WI6is
|  | 2024-03-01 | T3 status movie (March 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=MBeS8JQjowk
|  | 2024-04-01 | T3 status movie (April 2024), published on YT, LinkedIn, FB YT:
|  | 2024-05-01 | T3 status movie (May 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=z6tszmfwUc4&t=3s
|  | regular update | Subpage dedicated to T3 project is implemented on main BHCT website https://baltichub.com/inwestycje/projekt-t3 https://baltichub.com/en/investments/project-t3
|  | regular update | T3 status in all presentations for conferences and meetings with clients
|  | 2024-06-01 | BHCT poster with T3 status placed in neighbourhood districts
|  | 2024-06-01 | T3 poster on www https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/t3-status-budowy-czewiec-plakat
|  | 2024-06-01 | CFO update on T3 in TVP https://gdansk.tvp.pl/1467878/forum-panoramy
|  | 2024-06-01 | T3 status - LinkedIn https://www.linkedin.com/feed/update/urn:li:activity:7212094422514073601/?actorCompanyId=1203907
|  | (2024-06-05) | Cornerstone ceremony - the event incl. clients, stakeholders, local community representatives, media (wide media coverage) BHCT website: https://baltichub.com/aktualnosci-2/wmurowanie-kamienia-wegielnego-pod-budowe-nowego-nabrzeza-t3-w-baltic-hub LinkedIn: https://www.linkedin.com/feed/update/urn:li:ugcPost:7204159640060805120/?actorCompanyId=1203907
|  | 2024-08-01 | T3 status (June / July) - website Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/czerwiec-lipiec-status-budowy-t3
|  | (12.07.2024) | Meeting with district Councils re. T3 status and current issues 12.07.2024
|  | ongoing | BHCT website regular update: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3
|  | 2024-09-24 | Movie: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/wrzesien-2024-staus-prac-t3
|  | 2024-10-24 | Status: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/sierpien-wrzesien-status-budowy-t3 STS for T3: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/cztery-gigantyczne-suwnice-sts-dotarly-na-nabrzeze-t3-w-baltic-hub-2
|  | 2024-11-24 | Movie: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/listopad-2024-status-prac-t3-film Poster:https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/listopad-2024-status-budowy-t3-plakat
|  | ongoing | LinkedIn and FB regular update LinkedIn: https://www.linkedin.com/company/dctgdansk/ FB: https://www.facebook.com/BalticHubContainerTerminal/
|  | ongoing | regular contact with media and answering questions; publications review - IMM
|  | 2024-11-01 | T3 status poster on www and placed in local districts
|  | ongoing | LinkedIn and FB regular update LinkedIn: https://www.linkedin.com/company/dctgdansk/ FB: https://www.facebook.com/BalticHubContainerTerminal/
|  | ongoing | T3 status in every commercial presentation for clients
|  | 2025-02-01 | T3 test call Link: https://www.youtube.com/watch?v=xmzxX4O_JW4
|  | 2025-02-25 | T3 stattus of works Link: https://baltichub.com/en/investments/project-t3/news-t3/january-february-2025-t3-status-of-works
|  | 2025-03-25 | Final three STS cranes arrive at Baltic Hub Link: https://baltichub.com/en/investments/project-t3/news-t3/final-three-sts-cranes-arrive-at-baltic-hub
|  | 2025-03-25 | The first test of Ocean Going Vessel at T3 Link: https://baltichub.com/en/investments/project-t3/news-t3/first-test-of-an-ocean-going-vessel-at-the-t3-quay-in-baltic-hub
|  | 2025-04-25 | T3 status pof works Link: https://baltichub.com/en/investments/project-t3/news-t3/march-april-2025-t3-status-of-works
|  | 2025-06-01 | T3 official opening - an event attended by the media, government officials, top clients, and the local community Link: https://baltichub.com/en/news/baltic-hub-inaugurates-t3-terminal Movie: https://www.youtube.com/watch?v=LsoOPHBls10
|  | 2025-06-25 | T3 poster on www Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/status-budowy-t3-czerwiec-2025-plakat
|  | 2025-07-01 | T3 construction process https://baltichub.com/en/investments/project-t3/news-t3/t3-construction-process-11-2023-06-2025
|  | 2025-11-01 | T3 finalization of the project https://baltichub.com/en/investments/project-t3/news-t3/the-t3-project-at-baltic-hub-is-officially-completed
|  | 2025-11-25 | T3 poster on www
|  | 2026-06-26 | T3 poster on www
|  | ongoing | Information re. BHCT development

## 1.2
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 1 All external stakeholders (all-level authorities; local communities; vulnerable groups; other parties: NGOs, educational, mass media and community based organizations, etc. | 1.2 | Collect opinions and concerns during annual public meetings; | BHCT Project Team / Stakeholder Management Team / Communication Dept |  |  |  | x |  |  |  | x
|  | DATE | REMARKS
Collect opinions re. T3 project status by means of: - writting down the questions that have been raised by the participants of the meeting and then distributing the complied questions to those participants whose e-mail addresses we have
|  | (08.09.2022) | Meetings with local community (district councils) are planned for Spetember, 23rd
|  | (20.07.2022) | Dedicated e-mail address for people to contact DCT re. T3 development was prepared: T3-development@baltichub.com
|  | (29.08.2022) | Dedicated e-mail address for people to contact DCT re. T3 development was prepared: T3-development@baltichub.com and announced at posters, leaflets and in e-mail correspondence with district councils
|  | (23.11.2022) | Informational open meeting with districts residents re. T3 construction
|  | (24.11.2022) | Summary of the mtg with residents (portal - Gdansk City) https://gdansk.naszemiasto.pl/nowy-terminal-kontenerowy-w-gdansku-mieszkancy-mamy-do-was/ar/c1-9102045
|  | 17.04.2023 | Meeting with local community (district councils) on 17.04.20203
|  | July-August 2023 | Sumemr cinema and sport activities at Stogi beach for residents
|  | August 2023 | Safe on the beach - action with Dziennik Bałtycki
|  | September 2023 | Cleaning of the beach - action with Dziennik Bałtycki
|  | September 2023 | Marine fest for local residents - open doors https://www.youtube.com/watch?v=mrB37Kas6Kw
|  | (2023-10-01) | Meeting with District Councils re. T3 status and current issues 27.10.2023
|  | ongoing | Direct calls with District Councils
|  | (2024-06-08) | Festival organised by Stogi District Council for residents - BHCT informational point, eco workshop for kids, iceream; leaflets and poster with T3 status
|  | (2024-06-08) | Festival organised by Przerobka District Council for residents - BHCT sponsored theatre play for children
|  | 2024-06-01 | Cleaning of the beach - action with Dziennik Bałtycki planned for 18.06.2024 and Sep 2024
|  | regular | Monitoring opinions on Facebook
|  | (2024-06-08) | Festival organised by Stogi District Council for residents - BHCT informational point, eco workshop for kids, iceream; leaflets and poster with T3 status
|  | (2024-06-08) | Festival organised by Przerobka District Council for residents - BHCT sponsored theatre play for children
|  | 2024-06-01 | BHCT poster with T3 status placed in neighbourhood districts
|  | (2024-07-12) | Meeting with district councils re. T3 status and current issues 12 July 2024
|  | 2024-07-01 | Safe on the beach with Dziennik Bałtycki - educational action for residents and beachgoers
|  | 2024-08-01 | Safe on the beach with Dziennik Bałtycki - educational action for residents and beachgoers
|  | Jul/Aug 2024 | Summer cinema and sport activities planned for Jul-Aug 2024
|  | Jul/Aug 2024 | Summer cinema and sport activities organized by Baltic Hub and port of Gdansk
|  | (01.09.2024) | Marine fest for local residents - open doors ; Informational tent with BHCT employees onsite to answer all questions re. T3 / Informational poster re. T3 project
|  | 2024-11-24 | BHCT poster with T3 status placed in neighbourhood districts
|  | 2024-07-12 | Eve meeting with the district council Przerobka
|  | 2024-07-12 | Christmas meeting with Stogi residents - chcristmas gifts for children sponsored by BHCT
|  | 2024-10-12 | Christmas tree lighting together with Stogi district residentss at the request of Distric Council
|  | 17.02.2025 | Meeting with Przerobka District Council re. "Young Gardener Academy" and Christmas 2025
|  | 10.04.2025 | Meeting with GOS re. BeBot and Port Bin Shallow
|  | 16.04.2025 | Meeting with NCŻ re. Port Bin Shallow
|  | 25.04.2025 | Si-Island begining (Busole Project) - opening of a sensory integration studio at school and kindergarten complex no. 4 at Stogi District Link: https://www.youtube.com/watch?v=cBaLmbvyaVk LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7321526116337233920
|  | 27-28.04.2025 | Relay of Hope - charity action, BHCT pays 1PLN per km
|  | 30.04.2025 | Meeting with COSA (Diretor Rafał Zakrzewski)
|  | 08.05.2025 | Meeting with GOS re. improving atractivness and safety of Stogi Beach
|  | 17.06.2025 | (Busole) Get involved in the movement - ZSP No. 11, official completion of the project and opening of the gym and sports tournament; the meeting was attended by Przeróbka district councilor Ms. Ela Żmijewska and representatives of neighboring schools (Mr. Artur Jastrząb, Ms. Anna Kuchta); declaration to apply for the next edition of Busola
|  | 17.06.2025 | (Busole) Gdańsk Archipelag of Culture – dance performances and summary of the Busole Blitz project, end of the dance season (purchase of costumes and travel subsidies for tournaments); councilor Przeróki – Magdalena Radosz – was present at the meeting.
|  | 27.06.2025 | (Busole) Official unveiling of the mural at the Provincial and Municipal Public Library in Stogi, created by students of the Academy of Fine Arts; summary of a series of workshops for children and adults.
|  | ongoing | (Busole) Ostoja – project completion planned for August – integration festival for the local community
|  | 29.05.2025 | First employee volunteer initiative – gardening, planting plants, and painting benches at the Ostoja nursing home Link: https://www.linkedin.com/feed/update/urn:li:activity:7333872212011012097
|  | ongoing | ROD - improving water retention on plots + workshops - project delayed due to high water levels
|  | ongoing | (Busole) ZSP No. 3, Artur Jastrząb - opening of the music studio planned for September
|  | 15.04.2025 | First Lego League Final – program for schools from neighborhood districts; BHCT financial support; 3 schools taking part in the project (Stogi, Przerobka, Krakowiec-Gorki Zach) Link: https://www.youtube.com/watch?v=mIBiMot96Mk LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7317819004381732864
|  | winter/spring | BHCT finances physical education for School Pupils No 61 in Stogi in Drakkar big hall
|  | 06.06.2025 | T3 Official Opening with district councils presence Link: https://www.youtube.com/watch?v=LsoOPHBls10
|  | 31.08.2025 | Open doors for citizens - the end of summer with Baltic Hub https://www.youtube.com/watch?v=3wUZ3p3TVKA
|  | planned for 30.08.2026 | Open doors for citizens - the end of summer with Baltic Hub

## 1.3
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 1 All external stakeholders (all-level authorities; local communities; vulnerable groups; other parties: NGOs, educational, mass media and community based organizations, etc. | 1.3 | Publicly disclose Project documentation (SEP, ESAP, SIP, NTS) | BHCT Project Team / Stakeholder Management Team / Communication Dept | 2022-07-13 | 13.07.2022 (done) |  | x |  |  |  | x
|  | DATE | REMARKS
Public documents on T3 webpage
|  | (13.07.2022) | Documents were published at T3 subpage en. https://dctgdansk.pl/en/investments/project-t3/documentation-t3/ pl. https://dctgdansk.pl/inwestycje/projekt-t3/dokumentacja-t3/
|  | December 2023 | New webpage: https://baltichub.com/inwestycje/projekt-t3/dokumentacja-t3 https://baltichub.com/en/investments/project-t3/documentation-t3

## 1.4
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 1 All external stakeholders (all-level authorities; local communities; vulnerable groups; other parties: NGOs, educational, mass media and community based organizations, etc. | 1.4 | Publicly disclose relevant Project updates (Post news on the Company’s website) | BHCT Project Team / Stakeholder Management Team / Communication Dept |  |  |  | x |  |  |  | x
|  | DATE | REMARKS
Placing information on DCT website, T3 section
|  | (08.07.2022) | Post on the T3 subpage and mainpage re. Selecting contractors was published: https://dctgdansk.pl/en/news/dct-gdansk-selects-contractors-to-begin-works-for-the-t3-expansion-project/
|  | (29.08.2022) | Post on the T3 subpage and mainpage re. Purchase of semi-automated RTG cranes was published: https://dctgdansk.pl/en/news/purchase-of-semi-automated-rtg-cranes/
|  | (08.09.2022) | Post with poster re. beginning of T3 construction https://dctgdansk.pl/aktualnosci-t3/informacja-o-rozpoczeciu-budowy-t3/
|  | (28.11.2022) | Article on the T3 subpage and main Baltic Hub Page re. Beginning of T3 construction https://dctgdansk.pl/en/news/baltic-hub-ceremoniously-kicks-off-construction-of-its-third-terminal-in-gdansk-port/
|  | (02.01.2023) | Movie and information re. Status of T3 construction published on the T3 subpage and main Baltic Hub webpage https://dctgdansk.pl/en/news/status-of-t3-works-december-2022/
|  | (13.02.2023) | Movie and information re. Status of T3 construction published on the T3 subpage and main Baltic Hub webpage https://dctgdansk.pl/aktualnosci/status-prac-t3-luty-2023/
|  | (09.03.2023) | Nigth noise measurment: https://dctgdansk.pl/aktualnosci/nocny-pomiar-halasu-9-10-03-2023/
|  | March 2023 | March update in www https://dctgdansk.pl/aktualnosci-t3/marzec-2023-zagladamy-na-teren-budowy-terminala-t3-w-baltic-hub/
|  | (11.04.2023) | Movie re. T3 Status (October 2022 - February 2023) https://dctgdansk.pl/aktualnosci/t3-status-prac-pazdziernik-2022-luty-2023/
|  | April 2023 | April update on www https://dctgdansk.pl/aktualnosci-t3/kwiecien-2023-zagladamy-na-teren-budowy-terminala-t3-w-baltic-hub/
|  | (17.05.2023) | Photos pilling https://dctgdansk.pl/aktualnosci-t3/palowanie-nabrzeza/
|  | (17.05.2023) | Movie. T3 update (May 2023) https://dctgdansk.pl/aktualnosci-t3/migawka-z-budowy-t3-maj-2023/
|  | May 2023 | May Update on www https://dctgdansk.pl/aktualnosci-t3/maj-2023-zagladamy-na-teren-budowy-w-baltic-hub/
|  | (14.06.2023) | June - T3 photos https://dctgdansk.pl/aktualnosci/zdjecia-z-budowy-t3-czerwiec-2023/
|  | (19.06.2023) | Last 5 piles: https://dctgdansk.pl/aktualnosci/wbicie-ostatnich-5-pali/
|  | (26.06.2023) | T3 status movie: https://dctgdansk.pl/aktualnosci/terminal-t3-w-budowie-film/
|  | (05.07.2023) | Informational poster re. T3 published on www https://dctgdansk.pl/en/t3-news/informational-poster-t3-june-2023/
|  | (18.07.2023) | T3 status movie (July 2023): https://dctgdansk.pl/en/news/t3-status-of-works-july-2023/
|  | ongoing | T3 subpage - news published regularly https://dctgdansk.pl/en/investments/project-t3/news/
|  | ongoing | Facebook regular update: https://www.facebook.com/BalticHubContainerTerminal/
|  | ongoing | LinkedIn regular update: https://www.linkedin.com/company/1203907/admin/feed/posts/
|  | August 2023 | T3 status (August 2023): https://baltichub.com/en/news/24732/
|  | September 2023 | T3 status (September 2023): https://baltichub.com/en/t3-news/t3-status-of-works-september-2023/
|  | September 2023 | T3 status movie (September 2023) https://www.youtube.com/watch?v=usPCiuBqAok&t=1s
|  | Deceber 2023 | T3 posters - status of the construction placed in local districts
|  | 2024-01-01 | T3 status movie (January 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=4QIIHJqkOBE
|  | 2024-02-01 | T3 status movie (February 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=4c5Mz9WI6is
|  | 2024-03-01 | T3 status movie (March 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=MBeS8JQjowk
|  | 2024-04-01 | T3 status movie (April 2024), published on YT, LinkedIn, FB YT:
|  | 2024-05-01 | T3 status movie (May 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=z6tszmfwUc4&t=3s
|  | 2024-06-01 | dedicated subpage - regular update en. https://baltichub.com/en/investments/project-t3/news-t3 pl. https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3
|  | 2024-06-01 | T3 poster on www https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/t3-status-budowy-czewiec-plakat
|  | (2024-06-05) | Cornerstone ceremony - the event incl. clients, stakeholders, local community representatives, media (wide media coverage) BHCT website: https://baltichub.com/aktualnosci-2/wmurowanie-kamienia-wegielnego-pod-budowe-nowego-nabrzeza-t3-w-baltic-hub LinkedIn: https://www.linkedin.com/feed/update/urn:li:ugcPost:7204159640060805120/?actorCompanyId=1203907
|  | 2024-08-01 | T3 status (June / July) - website Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/czerwiec-lipiec-status-budowy-t3
|  | ongoing | BHCT website regular update: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3
|  | 2024-09-24 | Movie: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/wrzesien-2024-staus-prac-t3
|  | 2024-10-24 | Status: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/sierpien-wrzesien-status-budowy-t3 STS for T3: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/cztery-gigantyczne-suwnice-sts-dotarly-na-nabrzeze-t3-w-baltic-hub-2
|  | 2024-11-24 | Movie: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/listopad-2024-status-prac-t3-film Poster:https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/listopad-2024-status-budowy-t3-plakat
|  | 2025-12-01 | https://baltichub.com/en/investments/project-t3/news-t3/december-2024-t3-status-of-works
|  | 2025-02-25 | First Vessel Handled at the New T3 in Baltic Hub https://baltichub.com/en/investments/project-t3/news-t3/test-vessel-call-on-t3
|  | 2025-03-01 | January / February 2025 - T3 status of works https://baltichub.com/en/investments/project-t3/news-t3/january-february-2025-t3-status-of-works
|  | 2025-03-01 | Final three STS cranes arrive at Baltic Hub https://baltichub.com/en/investments/project-t3/news-t3/final-three-sts-cranes-arrive-at-baltic-hub
|  | 2025-03-01 | First Test of Ocean-Going Vessel https://baltichub.com/en/investments/project-t3/news-t3/first-test-of-an-ocean-going-vessel-at-the-t3-quay-in-baltic-hub
|  | 2025-04-01 | March / April 2025 - T3 status of works https://baltichub.com/en/investments/project-t3/news-t3/march-april-2025-t3-status-of-works
|  | 2025-06-01 | T3 Opening https://baltichub.com/en/news/baltic-hub-inaugurates-t3-terminal
|  | 2025-06-25 | T3 poster on www Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/status-budowy-t3-czerwiec-2025-plakat
|  | 2025-07-01 | T3 construction process https://baltichub.com/en/investments/project-t3/news-t3/t3-construction-process-11-2023-06-2025
|  | 2025-11-01 | T3 finalization of the project https://baltichub.com/en/investments/project-t3/news-t3/the-t3-project-at-baltic-hub-is-officially-completed
|  | 2025-11-25 | T3 poster on www
|  | 2026-04-01 | Record-Breaking March at Baltic Hub - https://baltichub.com/en/news/record-breaking-march-at-baltic-hub
|  | 2026-01-01 | Baltic Hub sums up the year: new terminal, connections, and record volume https://baltichub.com/en/news/baltic-hub-sums-up-the-year-new-terminal-connections-and-record-volume
|  | 2026-06-26 | T3 poster on www
|  | ongoing | Information re. BHCT development

## 1.5
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 1 All external stakeholders (all-level authorities; local communities; vulnerable groups; other parties: NGOs, educational, mass media and community based organizations, etc. | 1.5 | Register, analyse and address comments submitted online | BHCT Project Team / Stakeholder Management Team / Communication Dept |  |  |  | x |  |  |  | x
|  | DATE | REMARKS
Compliance dept is running register oc comments/ complainnts subbmitted via dedicated e-mail: T3-developmnet@baltichub.com / register is available on Baltic Hub website: https://dctgdansk.pl/wp-content/uploads/2023/06/T3-complaints-register_2.pdf
|  | ongoing | Grievance register available here: https://dctgdansk.pl/wp-content/uploads/2023/06/T3-complaints-register_2.pdf
|  | ongoing | New webpage: https://baltichub.com/en/investments/project-t3/grievance-t3 https://baltichub.com/inwestycje/projekt-t3/zazalenia-t3
|  | ongoing | Grievance register available here: https://baltichub.com/storage/uploads/289af7c1-1cbe-496d-94c7-0d065f2716ce/T3-complaints-register_2.pdf
|  | 2024-06-13 | no official complaints in 2024
|  | 2024-11-22 [KW] | no official complaints in H2 2024
|  | JUN-25 | no official complaints in H1 2025
letter from Ecological Club
letter from Mr. Łapszo
|  | 2025-07-25 | Information on the need to transfer the as-built documentation of Terminal T3 in order to complete the maritime navigation charts
|  | 2025-10-25 | Letter reminding of request to fund several projects of the Committee as compensation for the establishment of the terminal

## 2.1.
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 2 Local authorities | 2.1 | Jointly organize open doors and annual meetings to collect community feedback | BHCT Project Team and Communication Dept |  |  |  | x |  |  |  | x
|  | DATE | REMARKS
|  | (07.09.2022) | Comments from the internal mtg: to organize meeting at school / library; bus tour around terminal; photo site visit on the beach; representation from port authority / city needed; once a year at least; summer cinema - to be used as ommunication chanel - to arrange a company who is experienced CSR Info (to check), they know how to perform the stakeholders dialogue; CEC to be involved
|  | (31.08.2022) | Direct talks with Chairmans of the local district council re. Organizing open meeting for residents from Stogi district / events related to Grant Competition Busole (Welfare Senior Home "Ostoja" in Stogi district)
|  | (08.09.2022) | Direct talks with Chairmans of the local district council re. Organizing open meeting for residents from Przerobka district / events related to Grant Competition Busole (Primary school no.61 in Przerobka district)
|  | (23.09.2022) | Meeting with local community (district councils) on 23.09.2023
|  | (23.11.2022) | Informational open meeting with districts residents re. T3 construction
|  | (24.11.2022) | Summary of the mtg with residents (portal - Gdansk City) https://gdansk.naszemiasto.pl/nowy-terminal-kontenerowy-w-gdansku-mieszkancy-mamy-do-was/ar/c1-9102045
|  | (03.03.2023) | Meeting with Polish Ecological Club
|  | (17.04.2023) | Meeting with local community (district councils) on 17.04.2023
|  | (03.09.2023) | Open doors for local districts organized at BHCT premises - family fest; the event was attended by more than 1000 people
|  | (27.10.2023) | Meeting with District Councils re. T3 status and current issues 27.10.2023
|  | (12.12.2023) | Christmas Tree meeting 12.12.2023
|  | 2024-03-25 | Tree planting with local residents and foundation One More Tree https://www.youtube.com/watch?v=0InLxN-40HI&t=10s
|  | (2024-06-08) | Festival organised by Stogi District Council for residents - BHCT informational point, eco workshop for kids, iceream; leaflets and poster with T3 status https://baltichub.com/csr/aktualnosci-csr/baltic-hub-na-festynach-dzielnicowych
|  | (2024-06-08) | Festival organised by Przerobka District Council for residents - BHCT sponsored theatre play for children https://baltichub.com/csr/aktualnosci-csr/baltic-hub-na-festynach-dzielnicowych
|  | Jul/Aug 2024 | Summer cinema and sport activities planned for Jul-Aug 2024
|  | 2024-09-01 | Marine fest for local residents - open doors
|  | (12.07.2024) | Meeting with district Councils re. T3 status and current issues 12.07.2024
|  | (01.09.2024) | Marine fest for local residents - open doors ; Informational tent with BHCT employees onsite to answer all questions re. T3 / Informational poster re. T3 project
|  | Aug/Sep 24 | Meetings with local authorities (Port of Gdansk, GOSiR, Maritime office, President of Gdansk - planned ) re. social project for local districts / beach
|  | 17.02.2025 | Meeting with Przerobka District Council re. "Young Gardener Academy" and Christmas 2025
|  | 10.04.2025 | Meeting with GOS re. BeBot and Port Bin Shallow
|  | 15.04.2025 | First Lego League Final – program for schools from neighborhood districts; BHCT financial support; 3 schools taking part in the project (Stogi, Przerobka, Krakowiec-Gorki Zach) Link: https://www.youtube.com/watch?v=mIBiMot96Mk LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7317819004381732864
|  | 16.04.2025 | Meeting with NCŻ re. Port Bin Shallow
|  | 25.04.2025 | Si-Island begining (Busole Project) - opening of a sensory integration studio at school and kindergarten complex no. 4 at Stogi District Link: https://www.youtube.com/watch?v=cBaLmbvyaVk LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7321526116337233920
|  | 27-28.04.2025 | Relay of Hope - charity action, BHCT pays 1PLN per km
|  | 30.04.2025 | Meeting with COSA (Diretor Rafał Zakrzewski)
|  | 08.05.2025 | Meeting with GOS re. improving atractivness and safety of Stogi Beach
|  | 29.05.2025 | First employee volunteer initiative – gardening, planting plants, and painting benches at the Ostoja nursing home Link: https://www.linkedin.com/feed/update/urn:li:activity:7333872212011012097
|  | 06.06.2025 | T3 Official Opening with district councils presence Link: https://www.youtube.com/watch?v=LsoOPHBls10
|  | 31.08.2025 | Open doors for citizens - the end of summer with Baltic Hub https://www.youtube.com/watch?v=3wUZ3p3TVKA
|  | planned for 30.08.2026 | Open doors for citizens - the end of summer with Baltic Hub

## 2.2
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 2 Local authorities | 2.2 | Develop plans to support commitments to invest in the wider port area - Stogi beach, Przerobka district, etc. (Presentations / reports) | BHCT Project Team and Communication Dept |  |  |  | x |  |  |  | x
|  | DATE | REMARKS
|  | 2022 - ongoing | Busole Grant Competition: - 7 projecs currently ongoing. Projects responding to the social needs of local residents. website: https://dctgdansk.pl/csr/grant-dzielnicowy-busole/ projects: https://dctgdansk.pl/csr/grant-dzielnicowy-busole/grant-dzielnicowy-busole-projekty-2022/
- Movie: Busole - Ostoja Alpaki https://youtu.be/ac0L7vDhftc
- Movie: Primary School 61 - "Direction-Backyard 61" https://www.youtube.com/watch?v=oVD9GIGkdV0
- Movie: Art. Therapy - Macrame workshops, animal flow https://youtu.be/SjISAZgCBog
- Movie: Social Library https://youtu.be/rXU1EwcLce80
- Movie: Family Orienteering races with Almanak Brotherhood https://youtu.be/c7Uv-kAAf3w
- Movie: Sewroom https://youtu.be/VhAnKUOBsSo
- Movie: Rowing with Drakkar Club https://youtu.be/qBhSHiNlcsY
- Busole summary movie https://youtu.be/2vJHSoTI-JY
|  | (29.08.2022) | Direct talks with Chairmans of the local district council re. organizing open meeting for residents from Przerobka district during events related to Grant Competition Busole (Primary school no.61 in Przerobka district)
|  | (23.11.2022) | Informational open meeting with districts residents re. T3 construction
|  | (12.12.2022) | Skatepark on Przerobka Mtg - project chosen by residents in civic budget 2022; BH financial support of the project / contract attached
|  | (17.04.2023) | Meeting with local community (district councils) on 17.04.20203
|  | (02.06.2023) | Correspondence and direct talks with District Council re. Empty Pond revitalization (this pond is close to Stogi Beach and T3 investment) and christmas tree
|  | (31.05.2023) | II Distric Grant Busole results:
|  | done | Busole - chosen projects / contract signing: – Academic Sports Association Górki Zachodnie organizing “Sports summer camps for 50 children and young people aged 5-12 from the districts of Przeróbka, Stogi, Krakowiec-Górki Zachodnie” – Awake Hope Foundation with the project “Fairy Tale World Neighborhood House” – Social Welfare Home “Ostoja” with the project “SENIOR STOGI, or SENIOR Independent Creative Open Hospitable Innovative” – Polish Ecological Club Pomeranian District with the project “Survival of Nature – the art of survival between industry and man” – School and Preschool Complex No. 3 with the project “Eco-workshop” – School and Preschool Complex No. 11 in Gdańsk with the project “Green Integration” – Fit Lady Studio organizing classes “Women have power – self-defense and dance”
|  | June 2023 | Supporting eMOCja Hospice located in Stogi District (donation of a car for hospice needs, financial support for the event - coffe) - contract in progess
|  | June 2023 | Meeting with President of Gdansk to present company, development plans and BHCT engagement in local community's projects
|  | (25.06.2023) | Supporting the sport event (run arond the Empty Pond) for Stogi District Citizens (this pond is close to Stogi Beach and T3 investment)
|  | 2023-07-01 | Supporting Hospice eMOCja as a result of Moving for Charity action (ammount of collected minutes converted into money and donated for the hospice): https://www.linkedin.com/feed/update/urn:li:activity:7084156375781511168
|  | July-August | Summer sport activities and summer cinema July / August 2023 Link: https://www.youtube.com/watch?v=91hmAh7crHM (Cinema) Link: https://www.youtube.com/watch?v=OQd3T5ay0_Y (Sports)
|  | (17.07.2023) | Skatepark for Przerobka
|  | (23.08.2023) | Distric Creative Hub - project to support Social Library in Stogi Link: https://www.youtube.com/watch?v=0P5aaEw75UA&t=4s
|  | (06.12.2023) | Skatepark Przeróbka - handing over the construction site to the contractor https://gdansk.tvp.pl/74337285/w-gdansku-powstana-nowe-skateparki
|  | (12.12.2023) | Christmas tree for Stogi district at the request of Distric Council planned for December 2023
Busole Grant Project II edition: en. https://baltichub.com/en/csr/busole-2nd-edition-winning-projects pl. https://baltichub.com/spoleczenstwo/busole-ii-edycja-zwycieskie-projekty
Eco - Workshop https://www.youtube.com/watch?v=-URRwO_HaRI
Sport https://www.youtube.com/watch?v=m4-chtxlOFA&t=18s
Klasa pod chmurką https://www.youtube.com/watch?v=cqyDFlnyncg&t=46s
Selfdefence https://www.youtube.com/watch?v=K3DFtl3jqYo&t=3s
Bajkowy Świat https://www.youtube.com/watch?v=T4ClfxM5cis
Survival natury https://www.youtube.com/watch?v=V3qC6MKWDDs
|  | (2024-06-08) | Festival organised by Stogi District Council for residents - BHCT informational point, eco workshop for kids, iceream; leaflets and poster with T3 status https://baltichub.com/csr/aktualnosci-csr/baltic-hub-na-festynach-dzielnicowych
|  | (2024-06-08) | Festival organised by Przerobka District Council for residents - BHCT sponsored theatre play for children https://baltichub.com/csr/aktualnosci-csr/baltic-hub-na-festynach-dzielnicowych
|  | Q3 / Q4 2024 | Road repairs in the Stogi district at the request of the Stogi District Council
|  | (2024-06-18) | III edition of Busole Grant Competition https://baltichub.com/csr/busole-informacje
|  | (2024-08-09) | III edition of Busole Grant Competition - winners announcement https://baltichub.com/en/csr/busole-3rd-edition-winning-projects
|  | 2024-07-01 | Contact with bunker fans – purchasing a paint to renovate the bunkers near Baltic Hub
|  | 2024-07-01 | Support for Rescue and Fire Fighting Unit No. 2 in Gdansk is located near the old city on Siennicka Street. The Baltic Hub container terminal is part of the area protected by officers from the aforementioned Unit
|  | Jul/Aug 2024 | Summer cinema and sport activities organized by Baltic Hub and port of Gdansk
|  | 28/07/2024 | Safe on the beach with Dziennik Bałtycki - educational action for residents and beachgoers
|  | 23/08/2024 | Safe on the beach with Dziennik Bałtycki - educational action for residents and beachgoers
|  | Jul/Aug 2024 | Baltic Creativity Hub in Stogi Social Library – summer classes for children
|  | Jul/Aug-24 | Donation of furniture for local schools
|  | (01.09.2024) | Marine fest for local residents - open doors ; Informational tent with BHCT employees onsite to answer all questions re. T3 / Informational poster re. T3 project
|  | 2024-09-24 | Donation for Primary School no. 72 in Stogi – for buying 100 books for children in order to meet with their author
|  | 2024-09-01 | First Lego League – program for schools from neighborhood districts; BHCT financial support; 3 schools taking part in the project (Stogi, Przerobka, Krakowiec-Gorki Zach)
|  | 19-09-2024 | Cleanining of the beach with DB
|  | 25/10/2024 | Pomeranian Hospice Gala - BHCT
|  | 2024-10-01 | Donation for School No 72 for Santa’s Day Football Tournament
|  | 2024-10-01 | Donation for 'Swiatla i Cienie Foundation' - support for people with intellectual disabilities
|  | 2024-11-01 | Christmas tree for Przerobka district
|  | 2024-07-12 | Christmas meeting with Stogi residents - chcristmas gifts for children sponsored by BHCT
|  | 2024-07-12 | Eve meeting with the district council Przerobka
|  | 2024-10-12 | Christmas tree lighting together with Stogi district residentss at the request of Distric Council planned for December 2023
|  | 2024-12-01 | Christmas tree for provincial and municipal public library in Stogi district
|  | 2024-12-01 | Noble Parcel for family from BHCT neighbourhood
|  | ongoing | Busole III projects
|  | 27-28.04.2025 | Relay of Hope - charity action, BHCT pays 1PLN per km
|  | 29.05.2025 | First employee volunteer initiative – gardening, planting plants, and painting benches at the Ostoja nursing home Link: https://www.linkedin.com/feed/update/urn:li:activity:7333872212011012097
|  | 25.04.2025 | Si-Island begining (Busole Project) - opening of a sensory integration studio at school and kindergarten complex no. 4 at Stogi District Link: https://www.youtube.com/watch?v=cBaLmbvyaVk LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7321526116337233920
|  | 15.04.2025 | First Lego League Final – program for schools from neighborhood districts; BHCT financial support; 3 schools taking part in the project (Stogi, Przerobka, Krakowiec-Gorki Zach) Link: https://www.youtube.com/watch?v=mIBiMot96Mk LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7317819004381732864
Beach cleaning with Dziennik Bałtycki Link:
|  | Jul/Aug-25 | Summer Cinema at Stogi Beach - Project togeether with Port of Gdansk for tourists and Gdansk citizents
|  | ongoing | 2 port bins Shallow for marinas in Gdansk (NCŻ, COSA) and one port bin shallow for City of Gdansk
|  | ongoing | Port Bin XL to be installed near T3 Berth at Baltic Hub
|  | ongoing | Modernization of the playground at 3 Szpaki Street in Stogi - contract signed with City of Gdansk
|  | ongoing | 2 new hybrid cars for Pomeranian Hospice for Children - works ongoing
|  | ongoing | New Project - increasing the attractiveness and safety of Stogi beach
|  | ongoing | BeBot device to clean the beach -The device will be handed over to the Gdańsk Sports Center on July 8, 2025.
|  | ongoing | projector screen for the Stogi District Council
|  | 12.06.2025 | Gadgets for children for a meeting between seniors and children at the Ostoja nursing home
|  | 2025-09-25 | Busole 4th edition – to be announced at the end of August/beginning of September
|  | 2025-10-01 | 2 new hybrid cars for Pomeranian Hospice for Children - works ongoing https://baltichub.com/en/csr/csr-news/new-cars-for-the-pomorze-dzieciom-hospice
|  | 2025-07-25 | BeBot device to clean the beach -The device will be handed over to the Gdańsk Sports Center on July 8, 2025. https://baltichub.com/en/news/bebot-poland-s-first-autonomous-beach-cleaning-robot
|  | 2026-03-01 | Modernization of the playground at 3 Szpaki Street in Stogi - contract signed with City of Gdansk
|  | 2026-06-01 | Increasing the attractiveness and safety of Stogi beach https://baltichub.com/en/news/baltic-hub-is-enhancing-the-safety-appeal-and-accessibility-of-stogi-beach
|  | Jul-Aug-26 | Summer Cinema https://baltichub.com/en/csr/csr-news/summer-cinema-at-stogi-beach-2025
|  | Finalization Jun-2026 | 2 port bins Shallow for marinas in Gdansk (NCŻ, COSA) and one port bin shallow for City of Gdansk
|  | Finalization Jun-2026 | Port Bin XL to be installed near T3 Berth at Baltic Hub

## 3.1
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 3 National and regional authorities, in particular, inspection agencies responsible for environmental protection and health and safety | 3.1 | Submit regular reports with the frequency dictated by the authorities on compliance with national legislation and permits | BHCT Project Team and Safety |  |  |  | x
|  | DATE | REMARKS
|  | MK (07.09.2022) | Comments from the internal mtg: RDOŚ to send required reports based on environmental decision, re. birds, bats, mammals; agreemnets with ornitologist and chiroptorologyst - onging; T3 decision - we need to continue all requirements from T2 environmental decision; what kind of reports ? - Karolina to check and send
|  | KW (24.03.2023) | Ornithologist and chiroptologist reports delivered to RDOŚ
|  | KW [24.07.2023] | Reports to RDOŚ are send once a year (no change)
|  | KW [10.12.2023] | Report to be send begining of 2024
|  | KW [25.06.2024] | Annualy report regarding compensation beach handed over to RDOŚ on 07.02.2024
|  | KW [22.11.2024] | Report to be send begining of 2025
|  | KW [25.06.2025] | Annualy report regarding compensation beach handed over to RDOŚ on 01.08.2025
|  | KW [19.06.2026] | Next report to be handed over to RDOŚ in September 2026

## 4.1
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 4 Focused stakeholder engagement with Chief of the Seal Sanctuary of the Hel Marine Station of the Institute of Oceanography of Gdansk University | 4.1 | Discuss the proposed deviations from the JNCC protocol and their effectiveness in protection of marine mammals from project activity (meetings and consultations / minutes from the meeting) | BHCT Project team managed by external companies Budimex and DEME / Consultant | [7 empty] | x
* Within 60 days of project disclosure period and during construction and operation
|  | DATE | REMARKS
|  | MK (07.09.2022) | Comments from internal mtg: Budimex / DEME is consulting soft-start procedure (palling procedure); they are to send notes re. changing decision; the meeting was held (when?)
|  | KW (24.03.2023) | Contractor had contacted Seal Sanctuary in September 2022 to talk about soft start procedure, corespondence attached.
|  | KW [24.07.2023] | Seal Sanctuary has been contacted before starting piling works (no change)
|  | KW [10.12.2023[ | Seal Sanctuary has been contacted before starting dredging works in September 2023, ADD advised to be installed
|  | KW [25.06.2024] | A report prepared by Marine Statnion Underwater noise emitted during the piling works in the Baltic Hub T3 area and their impact on marine animals” showing measures of underwater noise during piling works - piling and other underwater works have been finished on the Investment.
|  | KW [22.11.2024] | Dredging finished, works are conducted only on land
|  | KW [19.06.2026] | Construction works finished, terminal is fully operational

## 5.1
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 5 Focused stakeholder engagement with local communities and vulnerable groups living in the project area | 5.1 | Analyse the local socio-economic conditions in the project area of influence, focus on vulnerable groups (presentations, leaaflets, community meetings) | BHCT representative / Consultant | [7 empty] | x
* Within 60 days of project disclosure period and during construction and operation
|  | DATE | REMARKS
|  | (07.09.2022) | Comments from internal mtg: Social - economic Report from Arup (to check local communities pointed in the report, local businesses and be in touch with them)
|  | 2021-12-01 | subpage dedicated to T3 project is implemented on main BHCT website
|  | 2022 - ongoing | Busole Grant Competition: - 7 projecs currently ongoing. Projects responding to the social needs of local residents. website: https://dctgdansk.pl/csr/grant-dzielnicowy-busole/ projects: https://dctgdansk.pl/csr/grant-dzielnicowy-busole/grant-dzielnicowy-busole-projekty-2022/
- Movie: Busole - Ostoja Alpaki https://youtu.be/ac0L7vDhftc
- Movie: Primary School 61 - "Direction-Backyard 61" https://www.youtube.com/watch?v=oVD9GIGkdV0
- Movie: Art. Therapy - Macrame workshops, animal flow https://youtu.be/SjISAZgCBog
- Movie: Social Library https://youtu.be/rXU1EwcLce80
- Movie: Family Orienteering races with Almanak Brotherhood https://youtu.be/c7Uv-kAAf3w
- Movie: Sewroom https://youtu.be/VhAnKUOBsSo
- Movie: Rowing with Drakkar Club https://youtu.be/qBhSHiNlcsY
- Busole summary movie https://youtu.be/2vJHSoTI-JY
|  | (23.09.2022) | Meetings with local community (district councils)
|  | (29.08.2022) | Posters and leaflets re. beginning of T3 construction were prepared and posted on notice boards in neighbourhood districts, in the library in Stogi and Przerobka
|  | (29.08.2022) | E-mail communication re. beginning of T3 construction was sent to district councils, neighbourhood libraries, Gdansk port authority,Social Media groups of Stogi District
|  | (08.07.2022) | Post on the T3 subpage and mainpage re. Selecting contractors was published: https://dctgdansk.pl/en/news/dct-gdansk-selects-contractors-to-begin-works-for-the-t3-expansion-project/
|  | (29.08.2022) | Post on the T3 subpage and mainpage re. Purchase of semi-automated RTG cranes was published: https://dctgdansk.pl/en/news/purchase-of-semi-automated-rtg-cranes/
|  | (08.09.2022) | Post on the T3 subpage and mainpage of T3 construction informational poster
|  | (31.08.2022) | Face to face talks with Chairmans of the local district council / events related to Grant Competition Busole (Welfare Senior Home "Ostoja" in Stogi district)
|  | (08.09.2022) | Face to face talks with Chairmans of the local district council / events related to Grant Competition Busole (Promary school no.61 in Przerobka district)
|  | (06.09.2022) | Direct phone call - Chairman of Stogi District Council (in relation to informational posters placed in a district, asking about any comments form people - till now no comments and questions)
|  | (06.09.2022) | Direct phone call - Library in Stogi (in relation to informational posters placed in a district, asking about any comments form people - till now no comments and questions)
|  | (08.12.2022) | Participation in Christmas meeting organized by Primary School no. 61 with Przerobka district concil presence
|  | (22.12.2022) | Participation in Christmas meeting organized by "Ostoja" social welfare home with Stogi district council presence
|  | (15.12.2022) | Participation in Christmas meeting organized by Primary School no. 72 with Stogi district council presence
|  | (03.03.2023) | Meeting with Polish Ecological Club
|  | (17.04.2023) | Meeting with local community (district councils) on 17.04.20203
|  | (31.05.2023) | II Distric Grant Busole results: https://dctgdansk.pl/aktualnosci/ii-edycja-konkursu-grantowego-busole-rozstrzygnieta/ https://dctgdansk.pl/en/news/results-of-the-2nd-edition-of-the-busole-grant-competition/
|  | ongoing | Busole - chosen projects / contract signing: – Academic Sports Association Górki Zachodnie organizing “Sports summer camps for 50 children and young people aged 5-12 from the districts of Przeróbka, Stogi, Krakowiec-Górki Zachodnie” – Awake Hope Foundation with the project “Fairy Tale World Neighborhood House” – Social Welfare Home “Ostoja” with the project “SENIOR STOGI, or SENIOR Independent Creative Open Hospitable Innovative” – Polish Ecological Club Pomeranian District with the project “Survival of Nature – the art of survival between industry and man” – School and Preschool Complex No. 3 with the project “Eco-workshop” – School and Preschool Complex No. 11 in Gdańsk with the project “Green Integration” – Fit Lady Studio organizing classes “Women have power – self-defense and dance”
|  | (03.09.2023) | Marine fest for local residents - open doors https://www.youtube.com/watch?v=mrB37Kas6Kw
|  | (27.10.2023) | Meeting with District Councils re. T3 status and current issues 27.10.2023
|  | (2024-06-08) | Festival organised by Stogi District Council for residents - BHCT informational point, eco workshop for kids, iceream; leaflets and poster with T3 status https://baltichub.com/csr/aktualnosci-csr/baltic-hub-na-festynach-dzielnicowych
|  | (2024-06-08) | Festival organised by Przerobka District Council for residents - BHCT sponsored theatre play for children https://baltichub.com/csr/aktualnosci-csr/baltic-hub-na-festynach-dzielnicowych
|  | Jul/Aug 2024 | Summer cinema and sport activities planned for Jul-Aug 2024
|  | 2024-09-01 | Marine fest for local residents - open doors
|  | 2024-06-01 | Busole Grant Project II edition - finalization: en. https://baltichub.com/en/csr/busole-2nd-edition-winning-projects pl. https://baltichub.com/spoleczenstwo/busole-ii-edycja-zwycieskie-projekty
Eco - Workshop https://www.youtube.com/watch?v=-URRwO_HaRI
Sport https://www.youtube.com/watch?v=m4-chtxlOFA&t=18s
Klasa pod chmurką https://www.youtube.com/watch?v=cqyDFlnyncg&t=46s
Selfdefence https://www.youtube.com/watch?v=K3DFtl3jqYo&t=3s
Bajkowy Świat https://www.youtube.com/watch?v=T4ClfxM5cis
Survival natury https://www.youtube.com/watch?v=V3qC6MKWDDs
|  | (2024-06-18) | III edition of Busole Grant Competition https://baltichub.com/csr/busole-informacje
|  | (2024-07-12) | Meeting with district councils organized 12 July 2024
|  | (2024-08-09) | III edition of Busole Grant Competition - winners announcement https://baltichub.com/en/csr/busole-3rd-edition-winning-projects
|  | 2024-07-01 | Safe on the beach with Dziennik Bałtycki - educational action for residents and beachgoers
|  | 2024-08-01 | Safe on the beach with Dziennik Bałtycki - educational action for residents and beachgoers
|  | Jul/Aug 2024 | Summer cinema and sport activities planned for Jul-Aug 2024
|  | Jul/Aug 2024 | Summer cinema and sport activities organized by Baltic Hub and port of Gdansk
|  | (01.09.2024) | Marine fest for local residents - open doors ; Informational tent with BHCT employees onsite to answer all questions re. T3 / Informational poster re. T3 project
|  | 2024-11-24 | BHCT poster with T3 status placed in neighbourhood districts
|  | 2024-07-12 | Eve meeting with the district council Przerobka
|  | 2024-07-12 | Christmas meeting with Stogi residents - chcristmas gifts for children sponsored by BHCT
|  | 2024-10-12 | Christmas tree lighting together with Stogi district residentss at the request of Distric Council planned for December 2023
|  | ongoing | Busole III projects
|  | 10.04.2025 | Meeting with GOS re. BeBot and Port Bin Shallow
|  | 15.04.2025 | First Lego League Final – program for schools from neighborhood districts; BHCT financial support; 3 schools taking part in the project (Stogi, Przerobka, Krakowiec-Gorki Zach) Link: https://www.youtube.com/watch?v=mIBiMot96Mk LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7317819004381732864
|  | 16.04.2025 | Meeting with NCŻ re. Port Bin Shallow
|  | 25.04.2025 | Si-Island begining (Busole Project) - opening of a sensory integration studio at school and kindergarten complex no. 4 at Stogi District Link: https://www.youtube.com/watch?v=cBaLmbvyaVk LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7321526116337233920
|  | 27-28.04.2025 | Relay of Hope - charity action, BHCT pays 1PLN per km
|  | 30.04.2025 | Meeting with COSA (Diretor Rafał Zakrzewski)
|  | 08.05.2025 | Meeting with GOS re. improving atractivness and safety of Stogi Beach
|  | 24.05.2025 | Terminal Tour for guides affiliated with the Polish Tourist and Sightseeing Society (PTTK)
|  | 29.05.2025 | First employee volunteer initiative – gardening, planting plants, and painting benches at the Ostoja nursing home Link: https://www.linkedin.com/feed/update/urn:li:activity:7333872212011012097
|  | Jul/Aug-25 | Summer Cinema at Stogi Beach - Project togeether with Port of Gdansk for tourists and Gdansk citizents
|  | 2025-11-01 | 2 port bins Shallow for marinas in Gdansk (NCŻ, COSA) and one port bin shallow for City of Gdansk
|  | 2025-12-01 | Port Bin XL to be installed near T3 Berth at Baltic Hub
|  | 2025-11-01 | Modernization of the playground at 3 Szpaki Street in Stogi - contract signed with City of Gdansk
|  | 2025-10-01 | 2 new hybrid cars for Pomeranian Hospice for Children https://www.youtube.com/watch?v=h5atRwWyHSE
|  | ongoing | New Project - increasing the attractiveness and safety of Stogi beach
|  | 2025-07-01 | BeBot device to clean the beach -The device handed over to the Gdańsk Sports Center on July 30, 2025. https://www.youtube.com/watch?v=D0iT4F16hZ4
|  | 31.08.2025 | Open doors meeting for local districts
|  | sep-2025 | Meeting with Pomorze Dzieciom Hospice
|  | 2025/2026 | New project - beach for people with disabilities
|  | 2025-09-25 | Busole 4th edition – to be announced at the end of August/beginning of September
|  | 2025-10-01 | 2 new hybrid cars for Pomeranian Hospice for Children - works ongoing https://baltichub.com/en/csr/csr-news/new-cars-for-the-pomorze-dzieciom-hospice
|  | 2026-03-01 | Modernization of the playground at 3 Szpaki Street in Stogi - contract signed with City of Gdansk
|  | 2026-06-01 | Increasing the attractiveness and safety of Stogi beach https://baltichub.com/en/news/baltic-hub-is-enhancing-the-safety-appeal-and-accessibility-of-stogi-beach
|  | Jul-Aug-26 | Summer Cinema https://baltichub.com/en/csr/csr-news/summer-cinema-at-stogi-beach-2025
|  | Finalization Jun-2026 | 2 port bins Shallow for marinas in Gdansk (NCŻ, COSA) and one port bin shallow for City of Gdansk
|  | Finalization Jun-2026 | Port Bin XL to be installed near T3 Berth at Baltic Hub
|  | planned for 30.08.2026 | Open doors for citizens - the end of summer with Baltic Hub

## 5.2
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 5 Focused stakeholder engagement with local communities and vulnerable groups living in the project area | 5.2 | Public consultation meetings to consult the local communities about their needs, views/concerns on project implementation and impacts provided via community initiatives (project leaflets) | Project team (questins) / Communications (organizning) | [7 empty] | x
* Prior to start of any activities on the development of the T3
|  | DATE | REMARKS
|  | 06.09.2022 | Direct call with District Council re. posters T3
|  | 06.09.2022 | Direct call with Social Library re. posters T3
|  | 06.09.2022 | Direct call with Port of Gdansk Spokesperson re. posters T3
|  | (07.09.2022) | Comments from internal mtg: to invite people for open doors; meeting at school; collect questions prior the meeting, QR code with questions on poster (2 weeks for analysing)
|  | (23.09.2022) | Meetings with local community (district councils)
|  | (08.12.2022) | Participation in Christmas meeting organized by Primary School no. 61 with Przerobka district concil presence
|  | (22.12.2022) | Participation in Christmas meeting organized by "Ostoja" social welfare home 61 with Stogi district concil presence
|  | (15.12.2022) | Participation in Christmas meeting organized by Primary School no. 72 with Stogi district concil presence
|  | (23.11.2022) | Informational open meeting with districts residents re. T3 construction
|  | (24.11.2022) | Summary of the mtg with residents (portal - Gdansk City) https://gdansk.naszemiasto.pl/nowy-terminal-kontenerowy-w-gdansku-mieszkancy-mamy-do-was/ar/c1-9102045
|  | (03.03.2023) | Mtg with Polish Ecological Club
|  | (17.04.2023) | Mtg with district councils
|  | (02.06.2023) | Direct call with District Council
|  | (03-09-2023) | Marine fest for local residents - open doors https://www.youtube.com/watch?v=mrB37Kas6Kw
|  | 2023-10-01 | Meeting with District Councils re. T3 status and current issues plannef for 27.10.2023
|  | ongoing | correspondence with Polish Ecological Club
|  | ongoing | correspondence with Social Committee for Saving the Beach and Budling a Resort on Stogi Island
|  | (2024-06-08) | Festival organised by Stogi District Council for residents - BHCT informational point, eco workshop for kids, iceream; leaflets and poster with T3 status https://baltichub.com/csr/aktualnosci-csr/baltic-hub-na-festynach-dzielnicowych
|  | (2024-06-08) | Festival organised by Przerobka District Council for residents - BHCT sponsored theatre play for children https://baltichub.com/csr/aktualnosci-csr/baltic-hub-na-festynach-dzielnicowych
|  | Jul/Aug 2024 | Summer cinema and sport activities planned for Jul-Aug 2024
|  | (2024-07-12) | Meeting with District Councils re. T3 status and current issues 12.07.2024
|  | 2024-07-01 | Safe on the beach with Dziennik Bałtycki - educational action for residents and beachgoers
|  | 2024-08-01 | Safe on the beach with Dziennik Bałtycki - educational action for residents and beachgoers
|  | Jul/Aug 2024 | Summer cinema and sport activities planned for Jul-Aug 2024
|  | Jul/Aug 2024 | Summer cinema and sport activities organized by Baltic Hub and port of Gdansk
|  | (01.09.2024) | Marine fest for local residents - open doors ; Informational tent with BHCT employees onsite to answer all questions re. T3 / Informational poster re. T3 project
|  | 2024-11-24 | BHCT poster with T3 status placed in neighbourhood districts
|  | 2024-07-12 | Eve meeting with the district council Przerobka
|  | 2024-07-12 | Christmas meeting with Stogi residents - chcristmas gifts for children sponsored by BHCT
|  | 2024-10-12 | Christmas tree lighting together with Stogi district residentss at the request of Distric Council planned for December 2023
|  | ongoing | Busole III projects
|  | 10.04.2025 | Meeting with GOS re. BeBot and Port Bin Shallow
|  | 15.04.2025 | First Lego League Final – program for schools from neighborhood districts; BHCT financial support; 3 schools taking part in the project (Stogi, Przerobka, Krakowiec-Gorki Zach) Link: https://www.youtube.com/watch?v=mIBiMot96Mk LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7317819004381732864
|  | 16.04.2025 | Meeting with NCŻ re. Port Bin Shallow
|  | 25.04.2025 | Si-Island begining (Busole Project) - opening of a sensory integration studio at school and kindergarten complex no. 4 at Stogi District Link: https://www.youtube.com/watch?v=cBaLmbvyaVk LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7321526116337233920
|  | 27-28.04.2025 | Relay of Hope - charity action, BHCT pays 1PLN per km
|  | 30.04.2025 | Meeting with COSA (Diretor Rafał Zakrzewski)
|  | 08.05.2025 | Meeting with GOS re. improving atractivness and safety of Stogi Beach
|  | 29.05.2025 | First employee volunteer initiative – gardening, planting plants, and painting benches at the Ostoja nursing home Link: https://www.linkedin.com/feed/update/urn:li:activity:7333872212011012097
|  | Jul/Aug-25 | Summer Cinema at Stogi Beach - Project togeether with Port of Gdansk for tourists and Gdansk citizents
|  | 2025-11-01 | 2 port bins Shallow for marinas in Gdansk (NCŻ, COSA) and one port bin shallow for City of Gdansk
|  | 2025-12-01 | Port Bin XL to be installed near T3 Berth at Baltic Hub
|  | 2025-11-01 | Modernization of the playground at 3 Szpaki Street in Stogi - contract signed with City of Gdansk
|  | 2025-10-01 | 2 new hybrid cars for Pomeranian Hospice for Children https://www.youtube.com/watch?v=h5atRwWyHSE
|  | ongoing | New Project - increasing the attractiveness and safety of Stogi beach
|  | 2025-07-01 | BeBot device to clean the beach -The device handed over to the Gdańsk Sports Center on July 30, 2025. https://www.youtube.com/watch?v=D0iT4F16hZ4
|  | 31.08.2025 | Open doors meeting for local districts
|  | sep-2025 | Meeting with Pomorze Dzieciom Hospice
|  | 2025/2026 | New project - beach for people with disabilities
|  | 27-28.04.2025 | Relay of Hope - charity action, BHCT pays 1PLN per km
|  | 30.04.2025 | Meeting with COSA (Diretor Rafał Zakrzewski)
|  | 08.05.2025 | Meeting with GOS re. improving atractivness and safety of Stogi Beach
|  | 29.05.2025 | First employee volunteer initiative – gardening, planting plants, and painting benches at the Ostoja nursing home Link: https://www.linkedin.com/feed/update/urn:li:activity:7333872212011012097
|  | 06.06.2025 | T3 Official Opening with district councils presence Link: https://www.youtube.com/watch?v=LsoOPHBls10
|  | 31.08.2025 | Open doors for citizens - the end of summer with Baltic Hub https://www.youtube.com/watch?v=3wUZ3p3TVKA
|  | planned for 30.08.2026 | Open doors for citizens - the end of summer with Baltic Hub

## 5.3
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 5 Focused stakeholder engagement with local communities and vulnerable groups living in the project area | 5.3 | External grievance mechanism and targeted group meetings, as necessary (Public grievance forms (distributed, published in the local media, posted on the Company’s web-site for printing out / downloading / electronic submitting) | Communications (tool) / Claims (register and coordination) | [5 empty] | x
|  | DATE | REMARKS
|  | (07.09.2022) | Comments from internal mtg: the register to be managed by Claims dept
|  | (09.09.2022) | External grievance mechanism is prepared and published at T3 subpage: Pl. https://dctgdansk.pl/inwestycje/projekt-t3/zazalenia-t3/ En. https://dctgdansk.pl/en/investments/project-t3/grievance-t3
|  | (13.01.2023) | Information re. grievance mechanism published at News section of T3
|  | (03.03.2023) | Grievience re. Noise T3/01/2023
|  | (03.03.2023) | Grievience re. Noise T3/02/2023
|  | (12.04.2023) | Grievience re. Noise T3/03/2023
|  | (12.04.2023) | Grievience re. Noise T3/04/2023
|  | (12.04.2023) | Grievience re. Noise T3/05/2023
|  | (12.04.2023) | Grievience re. Noise T3/06/2023
|  | (14.04.2023) | Grievience re. Noise T3/07/2023
|  | (18.04.2023) | Grievience re. Noise T3/08/2023
|  | (18.04.2023) | Grievience re. Noise T3/09/2023
|  | (21.04.2023) | Grievience re. Noise T3/10/2023
|  | April 2023 | Comliance register was pulished on the website; the register is updated regulary https://dctgdansk.pl/wp-content/uploads/2023/06/T3-complaints-register_2.pdf
|  | (15.05.2023) | Grievience re. Noise T3/11/2023
|  | (15.05.2023) | Grievience re. Noise T3/12/2023
|  | (06.07.2023) | Poster informing about greviance machanism for local districts
|  | (26.06.2023) | Poster informing about greviance machanism for contractor's employees
|  | (2023-10-23) | Presentation for District Councils including slide re. grievance form
|  | December 2023 | Grievance register available on new BHCT webpage: https://baltichub.com/storage/uploads/289af7c1-1cbe-496d-94c7-0d065f2716ce/T3-complaints-register_2.pdf
|  | as for 2024-06-27 | No official complaints in 2024
|  | 2024-06-01 | BHCT poster with T3 status to be placed in neighbourhood districts (incl. info re grievance mechanism)
|  | 2024-06-01 | BHCT poster with T3 status to be placed in neighbourhood districts (incl. info re grievance mechanism)
|  | as for 2024-11-27 | No official complaints in 2024
|  | KW [25.06.2025] | No official complaints in first part of 2025
|  | 2025-09-25 | T3 poster on www Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/status-budowy-t3-czerwiec-2025-plakat
|  | 2025-11-01 | T3 poster on www Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/zakonczenie-projektu-t3-plakat
|  | 2026-06-26 | T3 poster on www https://baltichub.com/en/investments/project-t3/news-t3

## 6.1
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 6 Focused stakeholder engagement with local businesses at Stogi beach | 6.1 | Individual meetings to notify the business owners at Stogi beach of the potential impacts from the Project that could impact the number of beach goers | Company representative / Project Team / Communications / Claims coordinator | [7 empty] | x
* Before and during construction period (targeted during 60 days of public disclosure), direct meetings on demand (or when needed) during operation
|  | DATE | REMARKS
|  | MK (07.09.2022) | Comments from internal mtg: posters re. open meeting for local business; questions to be collected prorior to the meeting
|  | MK (23.11.2022) | Informational open meeting with districts residents re. T3 construction
|  | 2023-09-01 | Marine fest for local residents - open doors https://www.youtube.com/watch?v=mrB37Kas6Kw
|  | December 2023 | No requests for individual meetings from business owners so far
|  | 2024-01-01 | No requests for individual meetings from business owners so far
|  | 2024-02-01 | No requests for individual meetings from business owners so far
|  | 2024-03-01 | No requests for individual meetings from business owners so far
|  | 2024-04-01 | No requests for individual meetings from business owners so far
|  | 2024-05-01 | No requests for individual meetings from business owners so far
|  | 2024-06-01 | No requests for individual meetings from business owners so far
|  | 2025-06-25 | No requests for individual meetings from business owners so far
|  | 2025-11-01 | No requests for individual meetings from business owners so far
|  | 2026-06-26 | No requests for individual meetings from business owners so far

## 6.2
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 6 Focused stakeholder engagement with local businesses at Stogi beach | 6.2 | Update regularly on planned activities | Company representative / Project Team / Communications / Claims coordinator | [7 empty] | x
* Before and during construction period (targeted during 60 days of public disclosure), direct meetings on demand (or when needed) during operation
|  | DATE | REMARKS
|  | (07.09.2022) | Comments from internal mtg: posters, leaflets, no sending info directly to people becouse of RODO (GDPR)
|  | (12.2021) | Subpage dedicated to T3 project is implemented on main DCT website
Link: Project T3 - Terminal Kontenerowy DCT (dctgdansk.pl)
|  | (29.08.2022) | Posters and leaflets re. beginning of T3 construction were prepared and posted on notice boards in neighborhood districts, in the library in Stogi and Przerobka
|  | (29.08.2022) | E-mail communication re. beginning of T3 construction was sent to district councils, neighborhood libraries, Gdansk port authority, Social Media groups of Stogi District
|  | (08.07.2022) | Post on the T3 subpage and main page re. Selecting contractors was published:
https://dctgdansk.pl/en/news/dct-gdansk-selects-contractors-to-begin-works-for-the-t3-expansion-project/
|  | (29.07.2022) | Post on the T3 subpage and main page re. Purchase of semi-automated RTG cranes was published:
https://dctgdansk.pl/en/news/purchase-of-semi-automated-rtg-cranes/
|  | (08.09.2022) | Post on the T3 subpage and main page of T3 construction informational poster
|  | (16.11.2022) | Economical report TVP (regional TV) https://gdansk.tvp.pl/64557614/odc-16112022
|  | (17.11.2022) | Post on SM, Baltic Hub webpage, Stogi forum re. open meeting with residents
|  | (28.11.2022) | Article on the T3 subpage and main Baltic Hub Page re. Beginning of T3 construction https://dctgdansk.pl/en/news/baltic-hub-ceremoniously-kicks-off-construction-of-its-third-terminal-in-gdansk-port/
|  | (28.11.2022) | News in Panorama (regional TV) https://gdansk.tvp.pl/64778519/rozbudowa-terminala-baltic-hub
|  | (30.11.2022) | Economical report TVP (regional TV) https://gdansk.tvp.pl/64831323/odc-30112022
|  | (06.12.2022) | Drone status of T3 construction together with Reporter24.pl (https://www.youtube.com/watch?v=16oxzfzrH_A&lc=Ugxc3f-1HjO29IAQEkl4AaABAg)
|  | (15.12.2022) | Interview with CEO re. T3 construction (Gospodarka Morska)
|  | (17.12.2022) | Drone status of T3 construction together with Reporter24.pl https://www.youtube.com/watch?v=xyPm1k7gWmI&t=24s
|  | (22.12.2022) | Drone status of T3 construction together with Reporter24.pl https://www.youtube.com/watch?v=OsFUkCiNMD4
|  | (02.01.2023) | Movie and information re. Status of T3 construction published on the T3 subpage and main Baltic Hub webpage https://dctgdansk.pl/en/news/status-of-t3-works-december-2022/
|  | (04.01.2023) | News in TVP (regional TV) re. Status of T3 construction https://gdansk.tvp.pl/65477788/baltic-hub-sie-powieksza-modernizacja-terminalu-nabiera-tempa
|  | JAN/FEB 2023 | Leaflets and posters campaign re. I stage of construction and grievance mechanism
|  | 10.02.2023 | Posters and leaflets re. status of T3 construction were prepared and posted on notice boards in neighbourhood districts, in the library in Stogi and Przerobka
|  | 17.03.2023 | FB T3 update photos
|  | 17.04.2023 | Meeting with Distric Councils
|  | April-May 2023 | Correspondence with Distric Council and citizens re. Noise (answering complaints)
|  | 17.05.2023 | FB T3 hiperlapse https://fb.watch/lDqOtNA_Zu/
|  | 19.05.2023 | FB Post T3 update May
Direct talks re. Christmas tree with District Council
|  | 28.05.2023 | article gdansk.pl re. T3 construction https://www.gdansk.pl/wiadomosci/Stogi-Koniec-glosnego-uporczywego-palowania,a,243946
|  | 30.05.2023 | FB short movie aRTG: https://fb.watch/lDqAWx3BR5/
|  | 23.06.2023 | FB short movie T3: https://fb.watch/lDqveLw5lq/
|  | 26.06.2023 | Poster informing/ reminding re. Greviance form (placed in Budimex social rooms, on construction site, on the beach
|  | 30.06.2023 | Sustainability Report for 2022 as a summary of BHCT annual performance - publication https://dctgdansk.pl/csr/raport-zrownowazonego-rozwoju/
article wnp.pl re. T3 construction
|  | July 2023 | article puls gdanska.pl
|  | June 2023 | article DopravniNoviny
|  | ongoing | Subpage dedicated to T3 project is implemented on main DCT website udpated regulary: https://dctgdansk.pl/en/investments/project-t3/news/
|  | 01.07.2023 | Fb post:https://fb.watch/lDqf6ER7zO/
|  | 17.07.2023 | Status of works: https://dctgdansk.pl/en/news/june-2023-t3-status-of-works/
|  | 18.07.2023 | FB: https://fb.watch/lSjvzCqpho/
|  | 18.07.2023 | LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7086965299324829697
|  | August 2023 | Status of works: https://baltichub.com/en/news/24732/
|  | September 2023 | Status of works: https://baltichub.com/en/t3-news/t3-status-of-works-september-2023/
|  | September 20203 | T3 status movie (september 2023) https://www.youtube.com/watch?v=usPCiuBqAok&t=2s
|  | December 2023 | T3 poster re. Construction status in local district
|  | 2024-01-01 | T3 status movie (January 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=4QIIHJqkOBE
|  | 2024-02-01 | T3 status movie (February 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=4c5Mz9WI6is
|  | 2024-03-01 | T3 status movie (March 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=MBeS8JQjowk
|  | 2024-04-01 | T3 status movie (April 2024), published on YT, LinkedIn, FB YT:
|  | 2024-05-01 | T3 status movie (May 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=z6tszmfwUc4&t=3s
|  | regular update | Subpage dedicated to T3 project is implemented on main BHCT website https://baltichub.com/inwestycje/projekt-t3 https://baltichub.com/en/investments/project-t3
|  | regular update | T3 status in all presentations for conferences and meetings with clients
|  | (2024-06-08) | Festival organised by Stogi District Council for residents - BHCT informational point, eco workshop for kids, iceream; leaflets and poster with T3 status
|  | (2024-06-08) | Festival organised by Przerobka District Council for residents - BHCT sponsored theatre play for children
|  | (2024-07-12) | Meeting with District Councils re. T3 status and current issues plannef for 12.07.2024
|  | (2024-06-05) | Cornerstone ceremony - the event incl. clients, stakeholders, local community representatives, media (wide media coverage) BHCT website: https://baltichub.com/aktualnosci-2/wmurowanie-kamienia-wegielnego-pod-budowe-nowego-nabrzeza-t3-w-baltic-hub LinkedIn: https://www.linkedin.com/feed/update/urn:li:ugcPost:7204159640060805120/?actorCompanyId=1203907
|  | ongoing | Regular update on www, LinkedIn and FB

## 6.3
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 6 Focused stakeholder engagement with local businesses at Stogi beach | 6.3 | Set up communication channels for businesses to report issues with their operations to BHCT | Company representative / Project Team / Communications / Claims coordinator | [7 empty] | x
* Before and during construction period (targeted during 60 days of public disclosure), direct meetings on demand (or when needed) during operation
|  | DATE | REMARKS
|  | MK (07.09.2022) | Comments from internal mtg: posters with contact details for complains; stand-by duty at DCT for stakeholders (1 hr at week for face to face mtg); greviance form, dedicated e-mail address, updates on website
|  | MK (12.2021) | Subpage dedicated to T3 project is implemented on main BHCT website
Link: Project T3 - Terminal Kontenerowy DCT (dctgdansk.pl)
|  | MK (29.08.2022) | Posters and leaflets re. beginning of T3 construction were prepared and posted on notice boards in neighborhood districts, in the library in Stogi and Przerobka
|  | MK (29.08.2022) | E-mail communication re. beginning of T3 construction was sent to district councils, neighborhood libraries, Gdansk port authority, Social Media groups of Stogi District
|  | MK (09.09.2022) | External grievance mechanism is prepared and published at T3 subpage:
Pl. https://dctgdansk.pl/inwestycje/projekt-t3/zazalenia-t3/
En. https://dctgdansk.pl/en/investments/project-t3/grievance-t3/
|  | MK (17.11.2022) | Post on SM, Baltic Hub webpage, district councils informational boards, Stogi forum, trojmiasto.pl,gdansk.pl, Przerobka forum, re. open meeting with residents https://www.trojmiasto.pl/raport/Spotkanie-informacyjne-dla-mieszkancow-ws-nabrzeza-rt281880.html https://www.facebook.com/groups/189296819110936/permalink/893367545370523 https://www.gdansk.pl/wiadomosci/Jak-bedzie-przebiegac-budowa-nabrzeza-do-przeladunku-kontenerow-Dowiesz-sie-na-spotkaniu-w-SP-72-Baltic-Hub,a,231986?fbclid=IwAR2nTm7C_LRmHctFeYaU0jbpN-74eGk9cSPivtEGKMdg7ExM1hXi2CnDBz8
|  | MK (23.11.2022) | Informational open meeting with districts residents re. T3 construction
|  | JAN/FEB 2023 | Leaflets and posters campaign re. I stage of construction and grievance mechanism
|  | 17.04.2023 | Meeting with local community (district councils) on 17.04.20203
|  | 26.06.2023 | Poster informing/ reminding re. Greviance form (placed in Budimex social rooms, on construction site, on the beach
|  | MK (2023-09-01) | Marine fest for local residents - open doors https://www.youtube.com/watch?v=mrB37Kas6Kw
|  | MK (2023-10-01) | T3 status movie (September 2023), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=usPCiuBqAok FB: https://fb.watch/nVSUVXpAi3/ LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7120719815895359488
|  | MK (2023-10-27) | Meeting with District Councils re. T3 status and current issues 27.10.2023
|  | MK (2023-12-08) | T3 posters - status of the construction placed in local districts
|  | (12-12-2023) | Christmas tree for Stogi district at the request of Distric Council planned for December 2023
|  | ongoing | Correspondence with Polish Ecological Club
|  | ongoing | Correspondence with Social Committee for Saving the Beach and Budling a Resort on Stogi Island
|  | ongoing | E-mail and phone communication with local distrcits
|  | (2024-07-12) | Meeting with District Councils re. T3 status and current issues plannef for 12.07.2024
|  | 2024-07-01 | Safe on the beach with Dziennik Bałtycki - educational action for residents and beachgoers
|  | 2024-08-01 | Safe on the beach with Dziennik Bałtycki - educational action for residents and beachgoers
|  | Jul/Aug 2024 | Summer cinema and sport activities planned for Jul-Aug 2024
|  | Jul/Aug 2024 | Summer cinema and sport activities organized by Baltic Hub and port of Gdansk
|  | (01.09.2024) | Marine fest for local residents - open doors ; Informational tent with BHCT employees onsite to answer all questions re. T3 / Informational poster re. T3 project
|  | 2024-11-24 | BHCT poster with T3 status placed in neighbourhood districts
|  | 2024-07-12 | Eve meeting with the district council Przerobka
|  | 2024-07-12 | Christmas meeting with Stogi residents - chcristmas gifts for children sponsored by BHCT
|  | 2024-10-12 | Christmas tree lighting together with Stogi district residentss at the request of Distric Council planned for December 2023
|  | 17.02.2025 | Meeting with Przerobka District Council re. "Young Gardener Academy" and Christmas 2025
|  | 10.04.2025 | Meeting with GOS re. BeBot and Port Bin Shallow
|  | 15.04.2025 | First Lego League Final – program for schools from neighborhood districts; BHCT financial support; 3 schools taking part in the project (Stogi, Przerobka, Krakowiec-Gorki Zach) Link: https://www.youtube.com/watch?v=mIBiMot96Mk LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7317819004381732864
|  | 16.04.2025 | Meeting with NCŻ re. Port Bin Shallow
|  | 25.04.2025 | Si-Island begining (Busole Project) - opening of a sensory integration studio at school and kindergarten complex no. 4 at Stogi District Link: https://www.youtube.com/watch?v=cBaLmbvyaVk LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7321526116337233920
|  | 27-28.04.2025 | Relay of Hope - charity action, BHCT pays 1PLN per km
|  | 30.04.2025 | Meeting with COSA (Diretor Rafał Zakrzewski)
|  | 08.05.2025 | Meeting with GOS re. improving atractivness and safety of Stogi Beach
|  | 02.06.2025 | The 65th anniversary of Primary School No. 61 in Przeróbka was celebrated by representatives of the Ostoja Social Welfare Home, the City of Gdańsk, the Board of Education, and nearby schools.
|  | 17.06.2025 | (Busole) Get involved in the movement - ZSP No. 11, official completion of the project and opening of the gym and sports tournament; the meeting was attended by Przeróbka district councilor Ms. Ela Żmijewska and representatives of neighboring schools (Mr. Artur Jastrząb, Ms. Anna Kuchta); declaration to apply for the next edition of Busola
|  | 17.06.2025 | (Busole) Gdańsk Archipelago of Culture – dance performances and summary of the Busole Blitz project, end of the dance season (purchase of costumes and travel subsidies for tournaments); councilor Przeróki – Magdalena Radosz – was present at the meeting.
|  | 27.06.2025 | (Compasses) Official unveiling of the mural at the Provincial and Municipal Public Library in Stogi, created by students of the Academy of Fine Arts; summary of a series of workshops for children and adults.
|  | ongoing | (Busole) Ostoja – project completion planned for August – integration festival for the local community
|  | 29.05.2025 | First employee volunteer initiative – gardening, planting plants, and painting benches at the Ostoja nursing home Link: https://www.linkedin.com/feed/update/urn:li:activity:7333872212011012097
|  | ongoing | ROD - improving water retention on plots + workshops - project delayed due to high water levels
|  | ongoing | (Busole) ZSP No. 3, Artur Jastrząb - opening of the music studio planned for September
|  | winter/spring | BHCT finances physical education for School Pupils No 61 in Stogi in Drakkar big hall
|  | 06.06.2025 | T3 Official Opening with district councils presence Link: https://www.youtube.com/watch?v=LsoOPHBls10
|  | 2025-06-25 | T3 poster on www and local districts Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/status-budowy-t3-czerwiec-2025-plakat
|  | ongoing | Regular update on www, LinkedIn and FB
|  | 31.08.2025 | Open doors for citizens - the end of summer with Baltic Hub https://www.youtube.com/watch?v=3wUZ3p3TVKA
|  | 2025-11-01 | T3 poster on www Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/zakonczenie-projektu-t3-plakat
|  | 2026-06-26 | T3 poster on www https://baltichub.com/en/investments/project-t3/news-t3

## 7.1
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 7 Other businesses in the project area | 7.1 | Formal meetings to discuss increased traffic flows from T3 | Company representative / Project Team / Communications
* Before and during construction period, direct meetings on demand (or when needed) during operation
|  | DATE | REMARKS
|  | (07.09.2022) | Comments from internal mtg: implement on demand
|  | (23.11.2022) | Informational open meeting with districts residents re. T3 construction
|  | (17.04.2023) | Meeting with local community (district councils) on 17.04.20203
|  | (2023-09-01) | Marine fest for local residents - open doors https://www.youtube.com/watch?v=mrB37Kas6Kw
|  | (2023-10-27) | Meeting with District Councils re. T3 status and current issues 27.10.2023
|  | ongoing | E-mail and phone communication with local distrcits
|  | (2024-07-12) | Meeting with District Councils re. T3 status and current issues plannef for 12.07.2024
Meeting with District Councils re. T3 status and current issues plannef for Feb/Mar 2024

## 7.2
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 7 Other businesses in the project area | 7.2 | Notifications on works stages and planned activities (letter, notification, company website) | Company representative / Project Team / Communications | [7 empty] | x
* Before and during construction period, direct meetings on demand (or when needed) during operation
|  | DATE | REMARKS
|  | 12.2021 | subpage dedicated to T3 project is implemented on main BHCT website
|  | (08.07.2022) | Post on the T3 subpage and mainpage re. Selecting contractors was published: https://dctgdansk.pl/en/news/dct-gdansk-selects-contractors-to-begin-works-for-the-t3-expansion-project/
|  | (29.08.2022) | Post on the T3 subpage and mainpage re. Purchase of semi-automated RTG cranes was published: https://dctgdansk.pl/en/news/purchase-of-semi-automated-rtg-cranes/
|  | (08.09.2022) | Post on the T3 subpage and mainpage of T3 construction informational poster
|  | (28.11.2022) | Article on the T3 subpage and main Baltic Hub Page re. Beginning of T3 construction https://dctgdansk.pl/en/news/baltic-hub-ceremoniously-kicks-off-construction-of-its-third-terminal-in-gdansk-port/
|  | (02.01.2023) | Movie and information re. Status of T3 construction published on the T3 subpage and main Baltic Hub webpage https://dctgdansk.pl/en/news/status-of-t3-works-december-2022/
|  | JAN/FEB 2023 | Planned - leaflets and posters campaign re. Istage of construction and grievance mechanism
|  | (13.02.2023) | Movie and information re. Status of T3 construction published on the T3 subpage and main Baltic Hub webpage https://dctgdansk.pl/aktualnosci/status-prac-t3-luty-2023/
|  | (10.02.2023) | Posters and leaflets re. status of T3 construction were prepared and posted on notice boards in neighbourhood districts, in the library in Stogi and Przerobka
|  | (17.03.2023 ) | FB T3 update photos
|  | (17.04.2023) | Meeting with Distric Councils
|  | April-May 2023 | Correspondence with Distric Council and citizens re. Noise (answering complaints)
|  | 17.05.2023 | FB T3 hiperlapse https://fb.watch/lDqOtNA_Zu/
|  | 19.05.2023 | FB Post T3 update May
|  | 28.05.2023 | article gdansk.pl re. T3 construction https://www.gdansk.pl/wiadomosci/Stogi-Koniec-glosnego-uporczywego-palowania,a,243946
|  | 30.05.2023 | FB short movie aRTG: https://fb.watch/lDqAWx3BR5/
|  | 23.06.2023 | FB short movie T3: https://fb.watch/lDqveLw5lq/
|  | 26.06.2023 | Poster informing/ reminding re. Greviance form (placed in Budimex social rooms, on construction site, on the beach
|  | 30.06.2023 | Sustainability Report for 2022 as a summary of BHCT annual performance - publication https://dctgdansk.pl/csr/raport-zrownowazonego-rozwoju/
article wnp.pl re. T3 construction
|  | July 2023 | article puls gdanska.pl
|  | June 2023 | article DopravniNoviny
|  | ongoing | Subpage dedicated to T3 project is implemented on main BHCT website udpated regulary: https://dctgdansk.pl/en/investments/project-t3/news/
|  | 01.07.2023 | Fb post:https://fb.watch/lDqf6ER7zO/
|  | ongoing | correspondence with Polish Ecological Club
|  | ongoing | correspondence with Social Committee for Saving the Beach and Budling a Resort on Stogi Island
|  | (03.09.2023) | Marine fest for local residents - open doors https://www.youtube.com/watch?v=mrB37Kas6Kw
|  | (27-10.2023) | Meeting with District Councils re. T3 status and current issues 27.10.2023
|  | 2024-01-01 | T3 status movie (January 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=4QIIHJqkOBE
|  | 2024-02-01 | T3 status movie (February 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=4c5Mz9WI6is
|  | 2024-03-01 | T3 status movie (March 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=MBeS8JQjowk
|  | 2024-04-01 | T3 status movie (April 2024), published on YT, LinkedIn, FB YT:
|  | 2024-05-01 | T3 status movie (May 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=z6tszmfwUc4&t=3s
|  | regular update | Subpage dedicated to T3 project is implemented on main BHCT website https://baltichub.com/inwestycje/projekt-t3 https://baltichub.com/en/investments/project-t3
|  | regular update | T3 status in all presentations for conferences and meetings with clients
|  | (2024-06-05) | Cornerstone ceremony - the event incl. clients, stakeholders, local community representatives, media (wide media coverage) BHCT website: https://baltichub.com/aktualnosci-2/wmurowanie-kamienia-wegielnego-pod-budowe-nowego-nabrzeza-t3-w-baltic-hub LinkedIn: https://www.linkedin.com/feed/update/urn:li:ugcPost:7204159640060805120/?actorCompanyId=1203907
|  | (2024-06-27) | T3 status - LinkedIn https://www.linkedin.com/feed/update/urn:li:activity:7212094422514073601/?actorCompanyId=1203907
|  | ongoing | LinkedIn and FB regular update LinkedIn: https://www.linkedin.com/company/dctgdansk/ FB: https://www.facebook.com/BalticHubContainerTerminal/
website regular update
|  | ongoing | regular contact with media and answering questions; publications review - IMM
|  | 2024-11-24 | T3 status poster on www and placed in local districts
|  | ongoing | T3 status in every commercial presentation for clients
|  | 2025-02-01 | T3 test call Link: https://www.youtube.com/watch?v=xmzxX4O_JW4
|  | 2025-02-25 | T3 stattus of works Link: https://baltichub.com/en/investments/project-t3/news-t3/january-february-2025-t3-status-of-works
|  | 2025-03-25 | Final three STS cranes arrive at Baltic Hub Link: https://baltichub.com/en/investments/project-t3/news-t3/final-three-sts-cranes-arrive-at-baltic-hub
|  | 2025-03-25 | The first test of Ocean Going Vvessel at T3 Link: https://baltichub.com/en/investments/project-t3/news-t3/first-test-of-an-ocean-going-vessel-at-the-t3-quay-in-baltic-hub
|  | 2025-04-25 | T3 status pof works Link: https://baltichub.com/en/investments/project-t3/news-t3/march-april-2025-t3-status-of-works
|  | 2025-06-01 | T3 official opening - an event attended by the media, government officials, top clients, and the local community Link: https://baltichub.com/en/news/baltic-hub-inaugurates-t3-terminal Movie: https://www.youtube.com/watch?v=LsoOPHBls10
|  | 2025-06-25 | T3 poster on www Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/status-budowy-t3-czerwiec-2025-plakat
|  | 2025-11-01 | T3 poster on www Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/zakonczenie-projektu-t3-plakat
|  | 2026-06-26 | T3 poster on www https://baltichub.com/en/investments/project-t3/news-t3

## 8.1
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 8 Stogi beach visitors | 8.1 | Notify beach goers of any potential impacts from the Project (visual impacts, noise, light and water pollution,congestion of traffic coming into the area), during construction and operation (leaflets) | Project team / communications | [7 empty] | x
* Ongoing throughout construction and operation phase
|  | DATE | REMARKS
|  | (07.09.2022) | Comments from internal mtg: summer cinema to present info prior the movie; leaflets and posters, QR code questionaires
|  | (29.08.2022) | Posters and leaflets re. beginning of T3 construction were prepared and posted on notice boards in neighbourhood districts, in the library in Stogi and Przerobka
|  | (23.11.2022) | Informational open meeting with districts residents re. T3 construction
|  | JAN/FEB 2023 | Leaflets and posters campaign re. Istage of construction and grievance mechanism
|  | (10.02.2023) | Posters and leaflets re. status of T3 construction were prepared and posted on notice boards in neighbourhood districts, in the library in Stogi and Przerobka
|  | (12.04.2023) | Letter - Beachgoers counting by ZTM
|  | (26.06.2023) | Poster informing/ reminding re. Greviance form (placed in Budimex social rooms, on construction site, on the beach
|  | (06.07.2023) | Poster informing/ reminding re. Greviance form (placed on the Stogi beach)
|  | ongoing | Beachgoers counting: https://personalpr.sharepoint.com/:x:/g/Eez0BltV-UhFlZLYyHKjNPgB8L_5wS1jTaKBkRgul5uBZw?rtime=tGQIDIaH20g
|  | (18.07.2023) | Letter - Beachgoers counting by ZTM
|  | August 2023 | Safe on the beach - action with Dziennik Bałtycki
|  | September 2023 | Cleaning of the beach - action with Dziennik Bałtycki
|  | December 2023 | T3 poster re. Construction status in local district
|  | 2024-06-01 | BHCT poster with T3 status to be placed in neighbourhood districts and near the beach
|  | (18.07.2024) | Cleaning of the beach - action with Dziennik Bałtycki
|  | 2024-07-01 | Safe on the beach - action with Dziennik Bałtycki planned for July 2024
|  | 2024-08-01 | Safe on the beach - action with Dziennik Bałtycki planned for August 2024
|  | 2024-09-01 | Cleaning of the beach - action with Dziennik Bałtycki planned for September 2024
|  | 2024-11-01 | T3 status poster
|  | 2025-06-25 | T3 status poster
|  | 23.06.2025 | Second employee volunteer initiative - Beach cleaning with Dziennik Baltycki Link: https://dziennikbaltycki.pl/akcja-moj-baltyk-za-nami-razem-z-czytelnikami-posprzatalismy-plaze/ar/c1p2-27713719
|  | 2025-06-25 | T3 poster on www and on the board on the beach Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/status-budowy-t3-czerwiec-2025-plakat
|  | 2025-11-01 | T3 poster on www Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/zakonczenie-projektu-t3-plakat
|  | 2026-06-26 | T3 poster on www https://baltichub.com/en/investments/project-t3/news-t3

## 8.2
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 8 Stogi beach visitors | 8.2 | Notify the public about BHCT external Grievance Mechanism (public announcements at notice boards) | Project team / communications | [7 empty] | x
* Ongoing throughout construction and operation phase
|  | DATE | REMARKS
|  | (07.09.2022) | Comments from internal mtg: leaflets, webpage, posters
|  | (09.09.2022) | External grievance mechanism was prepared and published at T3 subpage: Pl. https://dctgdansk.pl/inwestycje/projekt-t3/zazalenia-t3/ En. https://dctgdansk.pl/en/investments/project-t3/grievance-t3
|  | (05.01.2023) | Information re. grievance mechanism published at News section of T3
|  | JAN/FEB 2023 | Leaflets and posters campaign re. I stage of construction and grievance mechanism
|  | (10.02.2023) | Posters and leaflets re. status of T3 construction were prepared and posted on notice boards in neighbourhood districts, in the library in Stogi and Przerobka
|  | (26.06.2023) | Poster informing/ reminding re. Greviance form (placed in Budimex social rooms, on construction site, on the beach
|  | (06.07.2023) | Poster informing/ reminding re. Greviance form (placed on the Stogi beach)
|  | (27.10.2023) | Meeting with District Councils re. T3 status and current issues 27.10.2023 incl. Info re grievance form
|  | December 2023 | T3 poster re. Construction status in local district incl. Info re grievance form
|  | (2024-06-08) | Festival organised by Stogi District Council for residents - BHCT informational point, eco workshop for kids, iceream; leaflets and poster with T3 status
|  | 2024-06-01 | BHCT poster with T3 status to be placed in neighbourhood districts incl. grievance e-mail
|  | 2024-11-01 | T3 status poster
|  | 2025-06-25 | T3 poster on www Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/status-budowy-t3-czerwiec-2025-plakat
|  | 2025-11-01 | T3 poster on www Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/zakonczenie-projektu-t3-plakat
|  | 2026-06-26 | T3 poster on www https://baltichub.com/en/investments/project-t3/news-t3

## 8.3
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 8 Stogi beach visitors | 8.3 | Post updated on the Project, specifically upcoming construction activities, on the Company’s website | Project team / communications | [7 empty] | x
* Ongoing throughout construction and operation phase
|  | DATE | REMARKS
|  | (12.2021) | Subpage dedicated to T3 project is implemented on main DCT website:
Link: Project T3 - Terminal Kontenerowy DCT (dctgdansk.pl)
|  | (08.07.2021) | Post on the T3 subpage and main page re. Selecting contractors was published:
https://dctgdansk.pl/en/news/dct-gdansk-selects-contractors-to-begin-works-for-the-t3-expansion-project/
|  | (29.08.2021) | Post on the T3 subpage and main page re. Purchase of semi-automated RTG cranes was published:
https://dctgdansk.pl/en/news/purchase-of-semi-automated-rtg-cranes/
|  | (08.09.2021) | Post on the T3 subpage and main page of T3 construction informational poster:
https://dctgdansk.pl/aktualnosci-t3/informacja-o-rozpoczeciu-budowy-t3/
|  | (28.11.2022) | Article on the T3 subpage and main Baltic Hub Page re. Beginning of T3 construction https://dctgdansk.pl/en/news/baltic-hub-ceremoniously-kicks-off-construction-of-its-third-terminal-in-gdansk-port/
|  | (02.01.2023) | Movie and information re. Status of T3 construction published on the T3 subpage and main Baltic Hub webpage https://dctgdansk.pl/en/news/status-of-t3-works-december-2022/
|  | 10.02.2023 | Posters and leaflets re. status of T3 construction were prepared and posted on notice boards in neighbourhood districts, in the library in Stogi and Przerobka
|  | 17.03.2023 | FB T3 update photos
|  | 17.04.2023 | Meeting with Distric Councils
|  | April-May 2023 | Correspondence with Distric Council and citizens re. Noise (answering complaints)
|  | 17.05.2023 | FB T3 hiperlapse https://fb.watch/lDqOtNA_Zu/
|  | 19.05.2023 | FB Post T3 update May
Direct talks re. Christmas tree with District Council
|  | 28.05.2023 | article gdansk.pl re. T3 construction https://www.gdansk.pl/wiadomosci/Stogi-Koniec-glosnego-uporczywego-palowania,a,243946
|  | 30.05.2023 | FB short movie aRTG: https://fb.watch/lDqAWx3BR5/
|  | 23.06.2023 | FB short movie T3: https://fb.watch/lDqveLw5lq/
|  | 26.06.2023 | Poster informing/ reminding re. Greviance form (placed in Budimex social rooms, on construction site, on the beach
|  | 30.06.2023 | Sustainability Report for 2022 as a summary of BHCT annual performance - publication https://dctgdansk.pl/csr/raport-zrownowazonego-rozwoju/
article wnp.pl re. T3 construction
|  | July 2023 | article puls gdanska.pl
|  | June 2023 | article DopravniNoviny
|  | ongoing | Subpage dedicated to T3 project is implemented on main DCT website udpated regulary: https://dctgdansk.pl/en/investments/project-t3/news/
|  | 01.07.2023 | Fb post:https://fb.watch/lDqf6ER7zO/
|  | 30.08.2023 | www T3 update T3: https://dctgdansk.pl/aktualnosci-t3/sierpnien-2023-status-budowy-t3/
|  | October 2023 | T3 October status
|  | December 2023 | T3 poster re. Construction status
|  | 2024-01-01 | T3 status movie (January 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=4QIIHJqkOBE
|  | 2024-02-01 | T3 status movie (February 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=4c5Mz9WI6is
|  | 2024-03-01 | T3 status movie (March 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=MBeS8JQjowk
|  | 2024-04-01 | T3 status movie (April 2024), published on YT, LinkedIn, FB YT:
|  | 2024-05-01 | T3 status movie (May 2024), published on YT, LinkedIn, FB YT: https://www.youtube.com/watch?v=z6tszmfwUc4&t=3s
|  | 2024-06-01 | dedicated subpage - regular update en. https://baltichub.com/en/investments/project-t3/news-t3 pl. https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3
|  | 2024-06-01 | T3 poster on www https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/t3-status-budowy-czewiec-plakat
|  | 2024-06-01 | T3 status - LinkedIn https://www.linkedin.com/feed/update/urn:li:activity:7212094422514073601/?actorCompanyId=1203907
|  | (2024-06-05) | Cornerstone ceremony - the event incl. clients, stakeholders, local community representatives, media (wide media coverage) BHCT website: https://baltichub.com/aktualnosci-2/wmurowanie-kamienia-wegielnego-pod-budowe-nowego-nabrzeza-t3-w-baltic-hub LinkedIn: https://www.linkedin.com/feed/update/urn:li:ugcPost:7204159640060805120/?actorCompanyId=1203907
|  | ongoing | BHCT website regular update: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3
|  | 2024-09-24 | Movie: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/wrzesien-2024-staus-prac-t3
|  | 2024-10-24 | Status: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/sierpien-wrzesien-status-budowy-t3 STS for T3: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/cztery-gigantyczne-suwnice-sts-dotarly-na-nabrzeze-t3-w-baltic-hub-2
|  | 2024-11-24 | Movie: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/listopad-2024-status-prac-t3-film Poster:https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/listopad-2024-status-budowy-t3-plakat
|  | ongoing | LinkedIn and FB regular update LinkedIn: https://www.linkedin.com/company/dctgdansk/ FB: https://www.facebook.com/BalticHubContainerTerminal/
|  | ongoing | T3 status in every commercial presentation for clients
|  | 2025-02-01 | T3 test call Link: https://www.youtube.com/watch?v=xmzxX4O_JW4
|  | 2025-02-25 | T3 stattus of works Link: https://baltichub.com/en/investments/project-t3/news-t3/january-february-2025-t3-status-of-works
|  | 2025-03-25 | Final three STS cranes arrive at Baltic Hub Link: https://baltichub.com/en/investments/project-t3/news-t3/final-three-sts-cranes-arrive-at-baltic-hub
|  | 2025-03-25 | The first test of Ocean Going Vessel at T3 Link: https://baltichub.com/en/investments/project-t3/news-t3/first-test-of-an-ocean-going-vessel-at-the-t3-quay-in-baltic-hub
|  | 2025-04-25 | T3 status pof works Link: https://baltichub.com/en/investments/project-t3/news-t3/march-april-2025-t3-status-of-works
|  | 2025-06-01 | T3 official opening - an event attended by the media, government officials, top clients, and the local community Link: https://baltichub.com/en/news/baltic-hub-inaugurates-t3-terminal Movie: https://www.youtube.com/watch?v=LsoOPHBls10
|  | 2025-06-25 | T3 poster on www Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/status-budowy-t3-czerwiec-2025-plakat
|  | 2025-07-01 | T3 construction process https://baltichub.com/en/investments/project-t3/news-t3/t3-construction-process-11-2023-06-2025
|  | 2025-11-01 | T3 finalization of the project https://baltichub.com/en/investments/project-t3/news-t3/the-t3-project-at-baltic-hub-is-officially-completed
|  | 2025-11-01 | T3 poster on www Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/zakonczenie-projektu-t3-plakat
|  | 2026-06-26 | T3 poster on www https://baltichub.com/en/investments/project-t3/news-t3

## 9.1
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 9 Other parties: NGOs, cultural, educational, mass media and community based organizations, military fans etc. | 9.1 | Booklets and progress leaflets | Company representative / Projet team / Communications | [6 empty] | x
* Ad-hoc meetings / communication, as needed
|  | DATE | REMARKS
|  | (07.09.2022) | Comments from internal mtg: WWF / Greenpeace -> info re. the first meetg was held on xx; they know how to contatc DCT
|  | (29.08.2022) | Posters and leaflets re. beginning of T3 construction were prepared and posted on notice boards in neighborhood districts, in the library in Stogi and Przerobka
|  | ongoing | Communication with mass media (press releasses re. T3 project)
|  | JAN/FEB 2023 | Leaflets and posters campaign re. Istage of construction and grievance mechanism
|  | 10.02.2023 | Posters and leaflets re. status of T3 construction were prepared and posted on notice boards in neighbourhood districts, in the library in Stogi and Przerobka
|  | 26.06.2023 | Poster informing/ reminding re. Greviance form (placed in Budimex social rooms, on construction site, on the beach
|  | 2023-07-01 | Poster informing about construction status and next steps preparde together with Budimex - in progress / will be printed out and distributed in July 2023
|  | December 2023 | T3 poster re. Construction status
|  | 2024-06-01 | BHCT poster with T3 status to be placed in neighbourhood districts
|  | 2024-06-01 | T3 poster on www https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/t3-status-budowy-czewiec-plakat
|  | ongoing | T3 status in all presentations for conferences and meetings with clients
|  | 2024-11-01 | T3 poster on www https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/listopad-2024-status-budowy-t3-plakat
|  | 2025-06-25 | T3 poster on www Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/status-budowy-t3-czerwiec-2025-plakat
|  | 2025-11-01 | T3 poster on www Link: https://baltichub.com/inwestycje/projekt-t3/aktualnosci-t3/zakonczenie-projektu-t3-plakat
|  | 2026-06-26 | T3 poster on www https://baltichub.com/en/investments/project-t3/news-t3

## 9.2
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 9 Other parties: NGOs, cultural, educational, mass media and community based organizations, military fans etc. | 9.2 | Individual meetings (on specific matters) | Company representative / Projet team / Communications | [6 empty] | x
* Ad-hoc meetings / communication, as needed
|  | DATE | REMARKS
Meetings at the request of NGO's
|  | 03.03.2023 | Meeting with Polish Ecological Club
|  | 18.05.2023 | Meeting with eMOCja Hospice
|  | 2023-05-01 | Sztafeta Nadziei - Pomeranian Hospice for Children / joint action of BHCT and Foundation to collect money for children
|  | 07.07.2023 | Meeting with Social Library and financial support for the Library's work
|  | 15.07.2023 | Meeting with eMOCja Hospice
|  | ongoing contact | Virtual Mtg with MARE foundation re. marine bins to be installed near T3 https://fundacjamare.pl/kosze-morskie/
|  | (2023-09-01) | Marine fest for local residents - open doors https://www.youtube.com/watch?v=mrB37Kas6Kw
|  | (2023-10-27) | Meeting with District Councils re. T3 status and current issues 27.10.2023
|  | (06.12.2023) | Support of St. Nicholas party for children from the Stogi district - handing over presents for children
|  | (2024-07-12) | Meeting with District Councils re. T3 status and current issues plannef for 12.07.2024
|  | Jul-Aug 2024 | Meeting with Social Library and financial support for the Library's work during holidays
|  | 2024-09-01 | Marine fest for local residents - open doors planned for 01.09.2024
|  | 17.02.2025 | Meeting with Przerobka District Council re. "Young Gardener Academy" and Christmas 2025
|  | 10.04.2025 | Meeting with GOS re. BeBot and Port Bin Shallow
|  | 15.04.2025 | First Lego League Final – program for schools from neighborhood districts; BHCT financial support; 3 schools taking part in the project (Stogi, Przerobka, Krakowiec-Gorki Zach) Link: https://www.youtube.com/watch?v=mIBiMot96Mk LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7317819004381732864
|  | 16.04.2025 | Meeting with NCŻ re. Port Bin Shallow
|  | 25.04.2025 | Si-Island begining (Busole Project) - opening of a sensory integration studio at school and kindergarten complex no. 4 at Stogi District Link: https://www.youtube.com/watch?v=cBaLmbvyaVk LinkedIn: https://www.linkedin.com/feed/update/urn:li:activity:7321526116337233920
|  | 27-28.04.2025 | Relay of Hope - charity action, BHCT pays 1PLN per km
|  | 30.04.2025 | Meeting with COSA (Diretor Rafał Zakrzewski)
|  | 08.05.2025 | Meeting with GOS re. improving atractivness and safety of Stogi Beach
|  | 29.05.2025 | First employee volunteer initiative – gardening, planting plants, and painting benches at the Ostoja nursing home Link: https://www.linkedin.com/feed/update/urn:li:activity:7333872212011012097
|  | 06.06.2025 | T3 Official Opening with district councils presence Link: https://www.youtube.com/watch?v=LsoOPHBls10
|  | 31.08.2025 | Open doors for citizens - the end of summer with Baltic Hub https://www.youtube.com/watch?v=3wUZ3p3TVKA
|  | 2026-06-26 | T3 poster on www

## 9.3
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 9 Other parties: NGOs, cultural, educational, mass media and community based organizations, military fans etc. | 9.3 | Email or phone communication (to be properly registered) | Company representative / Projet team / Communications | [6 empty] | x
* Ad-hoc meetings / communication, as needed
|  | DATE | REMARKS
|  | (07.09.2022) | Comments from internal mtg: all info in the project folder; Klaudia to create folder; to discuss with Adrian how it should look like; minutes from the meeting as a proof
|  | (29.08.2022) | E-mail communication re. beginning of T3 construction was sent to district councils, neighbourhood libraries, Gdansk port authority,Social Media groups of Stogi District
|  | (31.08.2022) | Face to face talks with Chairmans of the local district council / events related to Grant Competition Busole (Welfare Senior Home "Ostoja" in Stogi district)
|  | (08.09.2022) | Face to face talks with Chairmans of the local district council / events related to Grant Competition Busole (Primary school no.61 in Przerobka district)
|  | (06.09.2022) | Direct phone call - Chairman of Stogi District Council (in relation to informational posters placed in a district, asking about any comments form people - till now no comments and questions)
|  | (06.09.2022) | Direct phone call - Library in Stogi (in relation to informational posters placed in a district, asking about any comments form people - till now no comments and questions)
|  | (06.09.2022) | Direct phone call - Spokesperson of Port Authorithy (in relation to opinion from people re. T3 construction)
|  | (28.10.2022) | Direct phone call Chairman of Stogi District council re. T3 constuction site
|  | (24.11.2022) | Direct phone call Chairman of Stogi District council re. Presentation and additional questions after open mtg with district residents
|  | (30.11.2022) | E-mail with answers for additional questions after open mtg with district residents
|  | (30.11.2022) | Communication with Polish Ecological Club (letter)
|  | (01.12.2022) | Direct phone call Chairman of Stogi District council re. Additional questions after open mtg with district residents
|  | (08.12.2022) | Participation in Christmas meeting organized by Primary School no. 61 with Przerobka district concil presence
|  | (22.12.2022) | Participation in Christmas meeting organized by "Ostoja" social welfare home 61 with Stogi district concil presence
|  | (15.12.2022) | Participation in Christmas meeting organized by Primary School no. 72 with Stogi district concil presence
|  | (13.12.2022) | Request for public information regarding ferromagnetic reconnaissance work on the site and water body (sapper cleaning) - no official answer needed as BH is a private company; answer sent
|  | 31.01.2023 | Communication with Polish Ecological Club (BHCT response)
|  | 03.03.2023 | Meeting with Polish Ecological Club
|  | 26.05.2023 | Communication with Polish Ecological Club (BHCT response)
|  | 13.04.2023 | Communication with Mr. Łapszo (letter 1)
|  | 13.05.2023 | Communication with Mr. Łapszo (letter 2)
|  | 30.05.2023 | Communication with Mr. Łapszo (BHCT response)
|  | ongoing | Communication with bunkers fan re. revitalization of bunkers near BHCT
|  | 05.07.2023 | Phone communication with President of Stogi District
E-mail Communication with Stogi District re. noise
|  | 25.10.2023 | Communication with Mr. Łapszo (letter 3)
|  | 06.11.2023 | Communication with Polish Ecological Club (letter)
|  | 28.11.2023 | Communication with Polish Ecological Club (letter)
|  | ongoing | regular phone communication re. ongoing matters with distric councils (Stogi & Przeróbka)

## 10.1
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 10 Shareholders of the Company | 10.1 | Inform, consult, and involve in strategic decision making processes via constant reporting on project implementation status | Company Management | [7 empty] | x
* Monthly Steering committee/ Management Mtg, SBM (Qarterly)
|  | DATE | REMARKS
|  | ongoing | bi-weekly T3 internal mtgs for all involved in project
Managemnet Board Mtg (dates): 01.26 02.24 04.14 05.11 06.06 06.21 07.30 08.30 10.03 10.25 11.22 12.21
Supervisory Board Mtgs in 2023 (dates): 15.03, 22.06, 10.07, 12.07
Managemnet Board Mtg in 2024(dates): 25.01 ; 26.02; 28.03.; 25.04; 03.06.; 02.07
Supervisory Board Mtgs in 2024 (dates): 14.03; 06.06. ; 15.10; 12.12
Supervisory Board Mtgs in 2025 (dates): 14.02.2025, 27.05.2025, 11.09.2025, 17.12.2025
Steering Committee every 4th Wednesday of the month

## 10.2
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 10 Shareholders of the Company | 10.2 | Annual reports on project implementation status | Company Management | [7 empty] | x
* Monthly Steering committee/ Management Mtg, SBM (Qarterly)
|  | DATE | REMARKS
|  | ongoing | bi-weekly T3 internal mtgs for all involved in project
Managemnet Board Mtg (dates): 01.26 02.24 04.14 05.11 06.06 06.21 07.30 08.30 10.03 10.25 11.22 12.21
Supervisory Board Mtgs in 2023 (dates): 15.03, 22.06, 10.07, 12.07
Managemnet Board Mtg in 2024(dates): 25.01 ; 26.02; 28.03.; 25.04; 03.06.; 02.07
Supervisory Board Mtgs in 2024 (dates): 14.03; 06.06. ; 15.10; 12.12
Supervisory Board Mtgs in 2025 (dates): 14.02.2025, 27.05.2025, 11.09.2025, 02.12.2025

## 10.3
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 10 Shareholders of the Company | 10.3 | Project implementation status discussed on direct meetings | Company Management | [7 empty] | x
* Monthly Steering committee/ Management Mtg, SBM (Qarterly)
|  | DATE | REMARKS
|  | ongoing | bi-weekly T3 internal mtgs for all involved in project
Managemnet Board Mtg (dates): 01.26 02.24 04.14 05.11 06.06 06.21 07.30 08.30 10.03 10.25 11.22 12.21
Supervisory Board Mtgs in 2023 (dates): 15.03, 22.06, 10.07, 12.07
Managemnet Board Mtg in 2024(dates): 25.01 ; 26.02; 28.03.; 25.04; 03.06.; 02.07
Supervisory Board Mtgs in 2024 (dates): 14.03; 06.06. ; 15.10; 12.12
Supervisory Board Mtgs in 2025 (dates): 14.02.2025, 27.05.2025, 11.09.2025, 02.12.2025

## 10.4
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 10 Shareholders of the Company | 10.4 | Project implementation status discussed on shareholders board meetings | Company Management | [7 empty] | x
* Monthly Steering committee/ Management Mtg, SBM (Qarterly)
|  | DATE | REMARKS
Managemnet Board Mtg (dates): 01.26 02.24 04.14 05.11 06.06 06.21 07.30 08.30 10.03 10.25 11.22 12.21
Supervisory Board Mtgs in 2023 (dates): 15.03, 22.06, 10.07, 12.07
Managemnet Board Mtg in 2024(dates): 25.01 ; 26.02; 28.03.; 25.04; 03.06.; 02.07
Supervisory Board Mtgs in 2024 (dates): 14.03; 06.06. ; 15.10; 12.12
Supervisory Board Mtgs in 2025 (dates): 14.02.2025, 27.05.2025, 11.09.2025, 03.12.2025

## 11.1
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 11 Company employees | 11.1 | Inform employees about the Company Project plans in relation to labour issues | Project team and Communications / HR | [7 empty] | x
* Project specific training to take place before the start of any construction activities
|  | DATE | REMARKS
|  | (07.09.2022) | Comments from the internal mtg: Intranet, MR, CEO movies, events, mtgs with unions, LinkedIn
|  | (23.08.2022)) | Information on MR and Intranet re. T3 automatization
|  | (14.12.2022) | Post on MR - movie, summary of the year and plans for the future
|  | JAN/FEB 2023 | Leaflets and posters campaign re. Istage of construction and grievance mechanism
|  | (21.03.2022)) | Information/movie on MR and Intranet re. I phase of construction works
|  | ongoing | monthly update re. T3 construction on dedicated subpage on Intranet: https://intranet.ad.baltichub.com/dzial-projektow-i-infrastruktury
|  | ongoing | Monthly update re. T3 construction on dedicated subpage on Intranet: https://intranet.ad.baltichub.com/dziennik-budowy
|  | ongoing | Operational updates on. T3 Link: https://intranet.ad.baltichub.com/aktualnosci-t3

## 11.2
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 11 Company employees | 11.2 | Inform employees about the actual impacts on the local environment and communities | Project team and Communications / HR? | [7 empty] | x
* Project specific training to take place before the start of any construction activities
|  | DATE | REMARKS
|  | (07.09.2022) | Comments from the internal mtg: Intranet (dedicated T3 section), MR, CEO movies, events, mtgs with unions / publish environmental report
|  | 23.08.2022) | Information on MR and Intranet re. T3 automatization
|  | (14.12.2022) | Post on MR - movie, summary of the year and plans for the future
|  | JAN/FEB 2023 | Leaflets and posters campaign re. I stage of construction and grievance mechanism
|  | January 2023 | Baltic Hub News - article re.actual impact on local communities and CSR
|  | ongoing | monthly update re. T3 construction on dedicated subpage on Intranet: https://intranet.ad.baltichub.com/dzial-projektow-i-infrastruktury
|  | ongoing | Monthly update re. T3 construction on dedicated subpage on Intranet: https://intranet.ad.baltichub.com/dziennik-budowy
|  | ongoing | Operational updates on. T3 Link: https://intranet.ad.baltichub.com/aktualnosci-t3

## 11.3
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 11 Company employees | 11.3 | Include reference to the external grievance mechanism | Project team and Communications / HR | [7 empty] | x
* Project specific training to take place before the start of any construction activities
|  | DATE | REMARKS
|  | (07.09.2022) | Comments from internal mtg: Intranet, MR, CEO movies, events, mtgs with unions, to put the mechanism on Intranet
|  | JAN/FEB 2023 | Planned - leaflets and posters campaign re. Istage of construction and grievance mechanism
|  | January 2023 | Internal communication via MR and Intranet re. Grievance mechanism
|  | (10.01.2023) | Info on MR re. external grievance mechanism
|  | ongoing | Forms available on site

## 11.4
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 11 Company employees | 11.4 | Inform employees about the internal Project development issues, success and difficulties | Project team and Communications / HR
* Project specific training to take place before the start of any construction activities
|  | DATE | REMARKS
|  | (07.09.2022) | Comments from the mtg: Intranet, MR, CEO movies, events, mtgs with unions
|  | (23.05.2022) | Intranet post and MR informator re. Automation (semi Automated RTG-cranes)
|  | (23.05.2022) | CEO’s movie re. T3 Construction
|  | SEP 2022 | Next CEO’s movie re. T3 update planned for September
|  | ongoing | Communication via Intranet and MR
|  | November 2023 | Movie for employees re. Automatization on T3
|  | ongoing | Monthly update re. T3 construction on dedicated subpage on Intranet: https://intranet.ad.baltichub.com/dzial-projektow-i-infrastruktury
|  | ongoing | Monthly update re. T3 construction on dedicated subpage on Intranet: https://intranet.ad.baltichub.com/dziennik-budowy
|  | ongoing | Operational updates on. T3 Link: https://intranet.ad.baltichub.com/aktualnosci-t3

## 12.1
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 12 Contractors (on site) | 12.1 | Inform all contractors about DCT and EBRD requirements and commitments under the ESAP, SEP and otherrelevance management plans | Projct team / Contractor's representative |  |  |  | x |  | x |  | x
|  | DATE | REMARKS
|  | MK (07.09.2022) | Comments from the internal mtg: general contractor to inform how to contact other T3 contractors and sub-contractors
|  | KW (24.03.2023) | Contractor was informed by email on 18.07.2022, email attached
|  | KW [24.07.2023] | Contractor was informed before starting works, ESAP is live document updated every month
|  | KW [10.12.2023] | No changes
|  | KW [25.06.2024] | No changes
|  | KW [22.11.2024] | No changes
|  | KW [25.06.2025] | No changes
|  | KW [19.06.2026] | Construction works finished, terminal is fully operational

## 12.1.1
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 12 Contractors (on site) | 12.1.1 | Direct meetings and reporting | Company's representative / Contractor's representative |  |  |  | x |  | x |  | x
|  | DATE | REMARKS
|  | MK (07.09.2022) | Comments from internal mtg: Michal to think about it :) point in the report how it was done (general Contractor to answer)
|  | KW (24.03.2023) | Minutes from environmental meetings attached
|  | KW [24.07.2023] | Minutes from environmental meetings from first half of 2023 attached
|  | KW [10.12.2023] | Minutes from environmental meetings from second half of 2023 attached
|  | KW [25.06.2024] | Minutes from environmental meetings from first half of 2024 attached
|  | KW [25.11.2024] | Minutes from environmental meetings from second half of 2024 attached
|  | KW [19.06.2026] | Construction works finished, terminal is fully operational

## 12.1.2
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 12 Contractors (on site) | 12.1.2 | Contract requirements to be reflected in EPC contract as relevant based on DCT commitments under the ESAP | Company's representative / Contractor's representative |  |  |  | x |  | x |  | x
|  | DATE | REMARKS
|  | MK (07.09.2022) | Comments from internal mtg: EPC contract is signed
|  | KW (24.03.2023) | Informations are reflected in Contract in Schedule 8 Point 1.1.7.
|  | KW [24.07.2023] | Contractor is contractually obliged to fulfill EBRD requirements
|  | KW (10.12.2023} | No changes to the contract and requirements
|  | KW [25.06.2024] | Contractor is contractually obliged to fulfill EBRD requirements
|  | KW [25.11.2024] | No changes to the contract and requirements
|  | KW [25.06.2025] | No changes to the contract and requirements
|  | KW [19.06.2025] | Construction works finished, terminal is fully operational

## 12.1.3
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 12 Contractors (on site) | 12.1.3 | Monitoring, inspections and audits | Company's representative / Contractor's representative |  |  |  | x |  | x |  | x
|  | DATE | REMARKS
|  | MK (07.09.2022) | Comments from internal mtg: to check in SEP requiremnets
|  | KW (24.03.2023) | Reports from Baltic Hub's and Engineer's inspections added
|  | KW [24.07.2023] | updated internal H&S inspections, H&S monthly reports, HR inspections and engineer's H&S inspections for first half of 2023
|  | KW [10.12.2023] | updated internal H&S inspections, H&S monthly reports, HR inspections and engineer's H&S inspections for second half of 2023
|  | KW [26.06.2024] | updated for H1 24: HR inspections, H&S monthly report, HS internal audits, Engineer's HSE inspections
|  | KW [25.11.2024] | updated for H2 24: HR inspections, H&S monthly report, HS internal audits, Engineer's HSE inspections
|  | KW [25.06.2025 | updated for H1 25: HR inspections, H&S monthly report, HS internal audits, Engineer's HSE inspections
|  | KW [24.11.2025] | Updatet for H2 25: as above
|  | KW [19.06.2026] | Construction works finished, terminal is fuly operational

## 12.1.4
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 12 Contractors (on site) | 12.1.4 | Training and supervision | Company's representative / Contractor's representative |  |  |  | x |  | x |  | x
|  | DATE | REMARKS
|  | MK (07.09.2022) | Comments from internal mtg: to check in SEP requiremnets
|  | KW (24.03.2023) | Induction training and list of participants added
|  | KW [24.07.2023] | updated safety induction presentation for Deme and Budimex + list with bumber of participants
|  | KW [10.12.2023] | updated safety induction presentation
|  | KW [26.06.2024] | updated safety induction presentation
|  | KW [25.11.2024] | updated safety induction presentation
|  | KW [25.06.2025] | updated safety induction presentation
|  | KW [24.11.2025] | updated safety induction presentation
|  | KW [19.06.2026] | Construction works finished, terminal is fully operational, there is no more training

## 12.1.5
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 12 Contractors (on site) | 12.1.5 | Progress and incident reports | Company's representative / Contractor's representative |  |  |  | x |  | x |  | x
|  | DATE | REMARKS
|  | MK (07.09.2022) | Comments from internal mtg: to check in SEP requiremnets
|  | KW (24.03.2023) | Reports from incidents on T3 construction added
|  | KW [24.07.2023] | Updated list of incidents until end of June 2023
|  | KW [10.12.2023] | Updated list of incidents until November 2023
|  | KW [26.06.2024] | Updated list of incidents for H1 2024
|  | KW [25.11.2024] | Updated list of incidents for H2 2024
|  | KW [25.06.2025] | Updated list of incidents for H1 2025
|  | KW [24.11.2025] | No incidents in H2 25
|  | KW [19.06.2026] | Construction works finished, terminal is fully operational

## 13.1
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 13 Employees of the contractors | 13.1 | Inform the employees and contractors about labours and safety issues via direct meetings and information notes | Company's EHS officer - Mateusz Kaczyński | [7 empty] | x
* During construction, when contracting the construction companies(at least prior to start of any activities on site
|  | DATE | REMARKS
|  | MK (07.09.2022) | Comments from the internal mtg: Budimex to end the proof that it is performed correctly
|  | KW (24.03.2023) | Presentation from Induction meetings attached
|  | KW [24.07.2023] | Updated safety induction presentation and toolbox meetings
|  | KW [10.12.2023] | Updated safety induction presentation
|  | KW [26.06.2024] | Updated safety induction presentation
|  | KW [25.11.2024] | Updated safety induction presentation
|  | KW [25.06.2025] | Updated safety induction presentation
|  | KW [24.11.2025] | Updated safety induction presentation
|  | KW [19.06.2026] | Construction works finished, terminal is fully operational

## 13.2
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 13 Employees of the contractors | 13.2 | Training to include reference to workers grievance management system | Company's EHS officer - Mateusz Kaczyński | [7 empty] | x
* During construction, when contracting the construction companies(at least prior to start of any activities on site
|  | DATE | REMARKS
|  | MK (07.09.2022) | Comments from the internal mtg: Budimex to end the proof that it is performed correctly
|  | KW (24.03.2023) | Presentation from Induction meetings attached, there is a slide informing about grievance mechanism
|  | KW [24.07.2023] | updated presentation with slides informing about grievance mechanism
|  | KW [10.12.2023] | updated presentation with slides informing about grievance mechanism
|  | KW [26.06.2024] | updated presentation with slides informing about grievance mechanism
|  | KW [26.11.2024] | updated presentation with slides informing about grievance mechanism
|  | KW [25.06.2025] | updated presentation with slides informing about grievance mechanism
|  | KW [24.11.2025] | updated presentation with slides informing about grievance mechanism
|  | KW [19.06.2026] | Construction works finished, terminal is fully operational

## 13.3
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 13 Employees of the contractors | 13.3 | Training on project impacts and requirements to be organised as part of induction training for all employees | Company's EHS officer - Mateusz Kaczyński | [7 empty] | x
* During construction, when contracting the construction companies(at least prior to start of any activities on site
|  | DATE | REMARKS
|  | MK (07.09.2022) | Comments from the internal mtg: Budimex to end the proof that it is performed correctly
|  | KW (24.03.2023) | Presentation from Induction meetings attached
|  | KW [24.07.2023] | Presentation updated June 2023
|  | KW [10.12.2023] | Presentation updated December 2023
|  | KW [03.07.2024] | Presentation updated July 2024
|  | KW [25.11.2024] | Presentation updated November 2024
|  | KW [25.06.2025] | Presentation updated June 2025
|  | KW [19.06.2026] | Construction works finished, terminal is fully operational

## 13.4
Category |  | Nr | Task name | Responsibility | Start | Finish | Frequency | [5 empty] | Reference to original document
[7 empty] | Single | Annually | Quarterly | Monthly | Occasionaly | Regulary
CLICK TO GO BACK TO SEP |  |  | STAKEHOLDER ENGAGEMENT PLAN (SEP) | [9 empty] | ESAP
EXTERNAL STAKEHOLDERS | 13 Employees of the contractors | 13.4 | Training to refer to the external grievance management system. | Company's EHS officer - Mateusz Kaczyński | [7 empty] | x
* During construction, when contracting the construction companies(at least prior to start of any activities on site
|  | DATE | REMARKS
|  | MK (07.09.2022) | Comments from the internal mtg: Budimex to end the proof that it is performed correctly
|  | KW (24.03.2023) | Presentation from Induction meetings attached with a slide informing baout grievance mechanism
|  | KW [24.07.2023] | Updated presentation from Induction meetings attached with a slide informing baout grievance mechanism
|  | KW [10.12.2023] | Updated presentation from Induction meetings attached with a slide informing about grievance mechanism
|  | KW [03.07.2024] | Updated presentation from Induction meetings attached with a slide informing about grievance mechanism
|  | KW [25.11.2024] | Updated presentation from Induction meetings attached with a slide informing about grievance mechanism
|  | KW [25.06.2025] | Updated presentation from Induction meetings attached with a slide informing about grievance mechanism
|  | KW [24.11.2025] | Updated presentation from Induction meetings attached with a slide informing about grievance mechanism
|  | KW [19.06.2026] | Construction works finished, terminal is fully operational